## listing actions
Heading from national Route Map | Type | Milestone or point to consider |  | Actions |  |  | Reporting |  |  | Human resources needed |  |  |  |  | Financial resources needed |  |  |  | Sources of funds |  |  |  | Data |  |  |  | Accountability
|  |  | Responsible group | Narrative | Itemise tasks, e.g. submilestones | NC comments | RM target date | Own target date | Achievement target for Q3 2024 | in-house time | NZCO | DEO | NZCA | external input | costs of extra staff or consultants | capital costs | running costs | potential savings | From within the normal budget | A call on diocesan funds | Borrowing | Fundraising | Sources of data | Data in figures | Carbon emissions | Carbon emissions reporting dates | Who is the lead person? | What is the committee or group that is responsible for this work?
|  | Explanatory suggestions: |  | How relevant is this to you? What priority does it have? What difficulties does it pose? What do you want to say about it? | These might be steps along the way, or proportions achieved, or reportable KPIs. The steps might include investment decisions, policy changes, and using levers to change what others do. There might be options to appraise. | Your plan should make reference to the Practical Path to Net Zero, actively consider implementation of ‘quick wins’, how to decarbonise heat, how to reduce energy consumption and how to encourage behaviour change. | These are extracted from the national Route Map | These may differ from the national target dates if you judge that necessary | What might you report about your achievement on this milestone for the report the diocese must send? | How much extra time will this need? Will there be a need for extra staff? | time allocation in days over 2.5 years | time allocation in days over 2.5 years | time allocation in days over 2.5 years | These might be consultants, e.g. for expertise or a specialist project or survey | E.g. salary and/or contract costs for additional staffed support needed. | this might be for buildings' energy efficiency, new heating systems, or new renewable generation | this might be for renewable electricity supplies, electric vehicle leasing etc | What reduction in gross spend might you hope for from greater efficiency or local electricity generation or whatever? | By internal reallocation and savings, perhaps. This might also be by reallocation of staff time from other tasks | the diocese will need to think whether it can resource some of these extra costs and, if so, how. This might include internal 'loans'. There will probably be some sort of bidding process for very limited funds. It is anticipated that the national church will allocate funds to dioceses for capital expenditure in the next triennium. | Can a good case be made on the grounds of future savings? | Are there potential public grants, special loan schemes, charitable grants, special appeals. Can we be ready and prepared to put in sudden grant applications when opportunities arrive? | Either currently available or newly gathered. E.g. energy consumption from bills, EPC ratings of buildings, miles travelled by types of transport | Can you enter estimations what any of these numbers actually are? | Can these be estimated from known data, e.g. from fuel bills or mileage? | When might regular, or even irregular, recording dates for the data happen? Can a baseline be established? Is there useful historic data? | they will at least be responsible for communicating progress to the NZC Manager | And to whom does this committee report to?
4.1.0.1
4.1 Dioceses | Milestone | 4.1.1. Dioceses: All dioceses to convene a Net Zero Carbon working group, with senior representatives. | strategy |  | 1) invite members of NZC WG to first meeting // 2) invite new members to DETG and convene next meeting // 3) get NZC Admin to get dates into diaries |  | 2022+ | end 2023 |  | 5 meetings of each per year. Prep and attendance; admin | 25 | 20 | 30
4.1.0.2
4.1 Dioceses | Milestone | 4.1.2. Dioceses: All dioceses provide an annual carbon emissions report to Diocesan Synod using the results provided by the national Carbon Emissions report from Research and Statistics. | M&M & Comms | It is important the Communications Team support the Diocesan Environmental lead to produce an Annual Report that can articulate a clear message to a range of audiences that might read it - this can be used as a clear communications platform and point of reference in other communications. | Establish a yearly timeline and drafting plan for review, drafting, agreement and publication. | see my comments in line 5 | 2022+ |  |  | No extra Comms staff. On the assumption the Report is primmarily drafted by the environmental Lead, additional Comms time might equate to 20 hours. | 2 |  | 10 | One might take the view some additional external designer might be engaged to make a product more appealing on the eye. | Design work on a 20page report might equal £800. Diocesan environmental Officer required to produce main boby of report. |  |  |  |  | Will there be a Environmental cost 'pot' in addition to the staff investment from which these and other comms/marketing exspenses can be drawn from? == good point. We have not so far budgeted for one as I was not thinking it would come to a great deal. There should be some spare cash from the initial £15k grant |  |  | Use on national data. |  |  |  | Environemtal Lead supported by the Head of Communications | reporting upwards via DETG
4.1 Dioceses | Milestone | 4.1.2. Dioceses: All dioceses provide an annual carbon emissions report to Diocesan Synod using the results provided by the national Carbon Emissions report from Research and Statistics. | strategy | This suggests it should be an easy task of just pulling data off the national statistics. Underlying this though is the need to get people to send in their stats first | 1) NZC Admin to pull data together // 2) see other tabs for how to encourage people to enter data |  | 2022+ | 2024+
4.1 Dioceses | Milestone | 4.1.2. Dioceses: All dioceses provide an annual carbon emissions report to Diocesan Synod using the results provided by the national Carbon Emissions report from Research and Statistics. | parishes gen |  | record data from national DB | the EFT results should cover this | 2022+
4.1 Dioceses | Milestone | 4.1.2. Dioceses: All dioceses provide an annual carbon emissions report to Diocesan Synod using the results provided by the national Carbon Emissions report from Research and Statistics. | parish buildings | Happy to contribute to this on church buildings. | This is mainly EFT | This is mainly EFT // see strategy tab | 2022+
4.1 Dioceses | Milestone | 4.1.2. Dioceses: All dioceses provide an annual carbon emissions report to Diocesan Synod using the results provided by the national Carbon Emissions report from Research and Statistics. | housing | HLCs are no longer available to the Property Manager, but they only reveal energy spend, not carbon. It would be bettert to ask occupants for their energy use from which the carbon can be calculated | part of comms strategy - NOTE from GH: this is an annual thing isn't it? Same as doing the stats for mission forms and the EFT. Could we devise a "Sustainability Sunday" as a kind of festival, in which all churches are invited to take part? The Bishop's Advisers could even write a sermon on behalf of the Bishop?... A little effort for individual churches and clergy once a year.) // data inputting of results |  | 2022+
4.1 Dioceses | Milestone | 4.1.2. Dioceses: All dioceses provide an annual carbon emissions report to Diocesan Synod using the results provided by the national Carbon Emissions report from Research and Statistics. | glebe | Relevant - how does the measurement process compare with the requirements of companies act (on ltd companies)? It is only time until the Charity Commission requires some similar reporting by larger charities. | Identify from publically available information an estimate of carbon emissions from Glebe land. Question how to identify parochial owned trust land. | I think we are quite a way off being able to do this for glebe | 2022+ | 2024+ |  | Some input in establishing frameworks and decision processes |  |  |  | Land agents could give extra time to these elements of management. | possibly share with nieghbouring Dioceses? | n/a | n/a | n/a | current budgets |  |  |  | potentially only full data comes from tenants. | no | possibly (soil map) | Baseline can be established | Glebe Officer | Assets Sub committee
4.1 Dioceses | Milestone | 4.1.2. Dioceses: All dioceses provide an annual carbon emissions report to Diocesan Synod using the results provided by the national Carbon Emissions report from Research and Statistics. | VA schools | Noted to be considered as part of a wider strategy. | 1) persuade schools and use this as a motivator | how will be we get the data from schools? Answer - we persuade nearly all of them to use the Energy Footprint Toolkit | 2022+ | 2024 | [18 empty] | Jacqueline McCamphill
4.1.0.3
4.1 Dioceses | Milestone | 4.1.3. Dioceses: All dioceses develop a communication strategy to churches and schools - focus on the ‘why’, the theology, and make it positive. | M&M & Comms | The Communications and M&M team can by and large commit to the 'broadcast' communications around promoting best practice and helping towards communicating a 'workable' plan parishes and schools might be able to realise. What these teams cannot do is the full engagement with these entities in order to realise the on-the-ground change. This is where the overall net carbon plan that fully engages with change needs to sit ahead of the communications plan and where the Comms plan is then built on, in order to support and promote the extra people resources and other department workstreams that will realise these changes, based on the core central activities from the main plan. | It is anticipated that from the core main plan, a communicatiosn approach will be developed to build the messaging around the 5 marks of mission. Messaging needs to be acheivable. "if you do nothing else - do these 3 things". Parishes and schools with the resources (people and financial) and 'will' to do more will not need frequent Comms to push them along. The poorly resourced bodies will need guidance on the small things they can do with minimal time or cost needs. Milestones of measuring success should also be determined by the staff directly employed to support the environmental programme and how their job descriptions are realising successes (however minor). | I agree with your comments, but we need to make more of an action plan over this. I suggest something along these lines: // 1) NZC team develop an overarching message (using "focus on the ‘why’, the theology, and make it positive" and Five Marks Mission: make it BOTH/AND environment and mission) with the advice and feedback of the Comms and M&M teams 1A) NZC team to develop a ladder of potential parish actions from simple/easy to challenging/expensive, a bit like Practical Path to NZC, but simpler (our earlier 'One Small Step' might be a useful resource in developing this) 1B) NZC team will normally take the initiative in 'writing' messages, but consult with others 2) NZC team develop a timeline and drafting plan for specific messaging, e.g. EFT data inputting, Creationtide, EcoChurch campaign - with Comms support 3) Comms team identify channels for these various messages and the specific formats for each (style as well as detail like wordlength) 3A) all to consider how the messaging will flow from diocese to parish leaderships to congregations to communities 4) M&M and Comms teams review current messaging streams to see if any of these could incorporate environmental messages either occasionally or frequently, or, even, if any might be repurposed 5) establish a dedicated channel, eg newsletter, for engaged people to sign up to 6) schools largely a separate area under the Ed Team, but align with Parish School Missioner and the annual Lent Challenge 7) is there a role for deaneries? 8) the importance of people-to-people work - use DEO and Bps Climate Advisers, esp their networking hubs 9) work on internal communication among dicoesan departments 10) communicate the achievement and existence of the Action Plan itself! | 2022+ | Produce the Comms and Engagement Plan by close of 2023 (aasuming the main plan is in place on which to base the comms timeframes), with an annusl review in August of each year prioro to end of year Reporting of wider project to Synod. | Main Report and "3-page" comms/engagement summary plan and next steps | Three identified staff to be critical in contributing to the plan based on their defined work plans. // up front 20 hours to produce the plan, then 2-3 hours per week (across all comms activities) to deliver the messaging. | 10 | 10 | 10 | no | Yes met through funding of extra staff |  |  |  | Comms suppoort can come from within normal time budget. | If the communication messaging tools are produced in-house and/or shared no cost will be bought other than employee time. Production of outsourced materials requiring, for example, video or photography costs, will incur costs. == can you give any estimates for videography in particular? I believe there was some talk that Holli is good with videos; can she do them at little cost? |  |  | national and regional best practice, informned by the dedicated staff and the focus of the diocesan net zero carbon plan key objectives. (comms messaging to align with the strategy of the ncz plan objectives) |  |  |  | Head of Communications and deputy Director of M&M & Bp's advisers in liason with the Diocesan Env Officer. | reporting upwards via DETG
4.1.0.4
4.1 Dioceses | Milestone | 4.1.4. Dioceses: All dioceses provide an outline of their decarbonisation plans to Diocesan Synod as a Net Zero Carbon Action Plan, to include estimates of costs for different options, as well as the policy changes and levers for change required. To be reviewed annually by senior staff. The plan should make reference to the Practical Path to Net Zero and actively consider implementation of ‘quick wins’, how to decarbonise heat, how to reduce energy consumption and how to encourage behaviour change. | strategy |  | 1) initial action plan development underway // 2) annual review will need to be more than a review in the first years |  | 2023+ | 2023 and then 2024+ |  | 2) DEO 5d ; NZC 5d | 5 | 1 | 10
4.1.0.5
4.1 Dioceses | Milestone | 4.1.5. Dioceses: All dioceses audit clergy property (where possible) by 2023 and develop a property retrofitting plan by 2024 (see Section 4.4). | housing | Highly relevant. Significant time pressures. | 1) Audit: Complete EPCs all houses and then use these to tailor audits to particular houses // 2) Detailed audits; use varied specialists according to each house, eg electricians, ASHP installers [know of fully qualified installer], others [record: electrical installation; insulation levels; suitability for ASHP, suitablility for PV panels; secondary forms of heating; details of glazing; occupant's energy providers; expected changes to domestic building regs] // 3) Audit: design survey sheeets and IT input sheets to make sure key data is captured and easy to add to the property database. // 4) retrofit plan: develop this action point next year as the audit data comes in |  | 2023/24 | Property audit may slip to 2024. As a result retrofit plan may slip to 2025. Final retrofit plan may depend on availability of central church funding for PV/ASHP | Completed 50% property audit and begun plans for retrofit planning | 1) Commissioning of audits: 5 days // 2) Data entry: 0.5 days over 40 weeks // N.B there is a seaonal element to workload of the department, being especially high in the run up to Petertide, summer and Christmas holidays. [Already able to collect information using the specialisms of retained contractors] |  |  | 10 | Yes. Specialists to survey properties | 1) data input and admin provided by proposed NZC Admin Officer // 2) surveys: maybe as low as 2hr per property plus travel time. Budgeted estimate of £500 may be a little too high and so may not cost as much as £75,000 |  |  |  | small reallocation of HoD time to commission surveys | NZC grant for admin support and £30k for surveys. £44k provisionally noted as may be needed to complete surveys |  |  | EPC; clergy energy consumption bills | No | Could be estimate from fuel bills |  | Property Manager | Houses Sub-Committee responsible to Finance Committee
4.1.0.6
4.1 Dioceses | Milestone | 4.1.6. Dioceses: All dioceses audit their landholdings and develop a land management plan. | glebe | We have a management plan in place. It needs expanding to incorporate new ESG / NCZ objectives. Medium priority to be joined up with effective reporting | It is important to review the right measures / markers | I suspect a management plan will evolve as NZC and biodiv evolve. Might you be willing to share your work in progress with me for me to respond with a few thoughts? // the audit is much more of a biggie. You mention soil maps, but there is the whole idea we have been speaking of of using GIS to compile all this data together. The land agents and tenants could contribute a great deal to this data base, I suspect. | 2026 | 2025 | Well in hand if not complete | Should be achievable in the normal policy review process. |  |  |  | Surveyors? Is it part of the current management function? | believed n/a | n/a | n/a | none | possible | no | no | n/a | Soil Maps? | no | possibly to an extent | hopefully | Glebe Officer | Assets Sub committee
4.1.1.01
4.1 Dioceses | Every diocese should consider: | 1. Establishing a net zero carbon working group: Bring on board key stakeholders from all departments, bishops, archdeacons, and look for existing commitments and delivery of policy change. | strategy |  | see line 4 | see 4.1.0.1
4.1.1.02
4.1 Dioceses | Every diocese should consider: | 2. Gathering data and work to it: Task someone with creating an annual greenhouse gas emissions report using the data from Research and Stats, promote the Energy Footprint Tool and the Energy Toolkit, and the range of other national tools as they become available. | strategy |  | see line 5
4.1 Dioceses | Every diocese should consider: | 2. Gathering data and work to it: Task someone with creating an annual greenhouse gas emissions report using the data from Research and Stats, promote the Energy Footprint Tool and the Energy Toolkit, and the range of other national tools as they become available. | parish buildings | With the existing REACh data, and the potential for expansion of EFT uptake, dop we need to do other data gathering? People findit quite annoying… | see row 22 | see row 27 (new row number) |  |  |  | NZC 4d; admin 8d | 4 |  | 10
4.1 Dioceses | Every diocese should consider: | 2. Gathering data and work to it: Task someone with creating an annual greenhouse gas emissions report using the data from Research and Stats, promote the Energy Footprint Tool and the Energy Toolkit, and the range of other national tools as they become available. | VA schools | Refer to comments above regarding GEM's property management plan. | this will be done by the incoming NZCA | [7 empty] | 5
4.1.1.03
4.1 Dioceses | Every diocese should consider: | 3. Developing and agreeing a costed (costs and savings) strategy with Synod support. If possible, establish a local grant and/or loans scheme. | strategy |  | 1) see line 6 // 2) promoting tools, see other tabs
4.1.1.04
4.1 Dioceses | Every diocese should consider: | 4. Taking a two-pronged attack (i) finding some quick wins and pilots which show what is possible, while (ii) focussing strategically on the highest energy use buildings in the diocese, saving energy and decarbonising heat. | strategy | this should have been in the buildings tab! | 1) develop 'ladder of possibilities' see Comms tab // 2) identify either old cases or potential new ones of pilots or quick wins |  |  | 2024 |  | 1) NZC 2d; DAC 5d (admin replacement) | 2 |  | 5
4.1.1.05
4.1 Dioceses | Every diocese should consider: | 5. Commissioning a desk-based Renewable Energy Feasibility Study for all buildings. With the results, consider opportunities for bulk procurement by implementing solutions on an intervention basis (e.g. installing PV panels or heat pumps) rather than a building basis. Add to your diocesan Net Zero Carbon Action Plan | housing | The NZC team are investigating possibilites for bulk procurement, but procurement may need to be specific for each property. It may be more applicable to PV than to ASHPs | [6 empty] | 3
4.1 Dioceses | Every diocese should consider: | 5. Commissioning a desk-based Renewable Energy Feasibility Study for all buildings. With the results, consider opportunities for bulk procurement by implementing solutions on an intervention basis (e.g. installing PV panels or heat pumps) rather than a building basis. Add to your diocesan Net Zero Carbon Action Plan | strategy |  | see buildings tab
4.1 Dioceses | Every diocese should consider: | 5. Commissioning a desk-based Renewable Energy Feasibility Study for all buildings. With the results, consider opportunities for bulk procurement by implementing solutions on an intervention basis (e.g. installing PV panels or heat pumps) rather than a building basis. Add to your diocesan Net Zero Carbon Action Plan | parish buildings | Sample of buildings planned for study nuder NZC grant. Bulk procurement potential (not straightforward) for solar, pew heating, see Parish Buying. | desk-based study is unworkable; bulk procurement ditto | Desk based study of parish churches impossible as diocese does not have the data. // Instead will sample some of the top 20% using NZC funding. // bulk procurement largely under Parish Buying // but possibility of working with an entrepreneur to explore e.g. solar panel procurement
4.1 Dioceses | Every diocese should consider: | 5. Commissioning a desk-based Renewable Energy Feasibility Study for all buildings. With the results, consider opportunities for bulk procurement by implementing solutions on an intervention basis (e.g. installing PV panels or heat pumps) rather than a building basis. Add to your diocesan Net Zero Carbon Action Plan | VA schools | Assessed all VA schools (Cambs CC) and 6 schools selected that justify a business case for renewable energy solutions - via SALIX and Cambs CC funding. | 1) assess VA schools in Norfolk | this is a great achievement |  | 2025? | [18 empty] | Jacqueline McCamphill | Diocesan Board of Education
4.1 Dioceses | Every diocese should consider: | 5. Commissioning a desk-based Renewable Energy Feasibility Study for all buildings. With the results, consider opportunities for bulk procurement by implementing solutions on an intervention basis (e.g. installing PV panels or heat pumps) rather than a building basis. Add to your diocesan Net Zero Carbon Action Plan | DMAT | It is relevant but will always take less of a priority than addressing any serious and major capital projects to keep a school safe, warm and dry. Only beneficial if assessors have adequate experience, technical knowledge and are independent of manufacturers / suppliers of 'green energies'. This means excluding 'free' surveys offered by companies. Assessments of any value will have a cost attached to them. It appears local councils are guided by companies with a vested interest in selling green technologies and building assessments have not always been carried out with due diligence.
4.1.1.06
4.1 Dioceses | Every diocese should consider: | 6. Increasing capacity and understanding: potentially use the national ‘train the trainer’ scheme in Carbon Literacy to increase understanding across the diocese. | M&M & Comms | Ensure the national training webinars to improve knbowledge are widely shared in the comms materials. | Activities should be scheduled through internal comms channels throughout the year. Comms messaging will be determined by the focus of the NCZ plan and the messaging around supporting that. | 1) include general climate and carbon literacy messages (not forgetting the nature crisis as well) in the Comms Strategy; probably not use the Train the trainer scheme | [5 empty] | 3
4.1 Dioceses | Every diocese should consider: | 6. Increasing capacity and understanding: potentially use the national ‘train the trainer’ scheme in Carbon Literacy to increase understanding across the diocese. | strategy |  | see Comms tab
4.1.1.07
4.1 Dioceses | Every diocese should consider: | 7. Identifying required policy changes/levers for change: Create a DAC policy, set expectations for APCM reports, quinquennial inspections and archdeacon’s visitations. | strategy |  | see other tabs
4.1 Dioceses | Every diocese should consider: | 7. Identifying required policy changes/levers for change: Create a DAC policy, set expectations for APCM reports, quinquennial inspections and archdeacon’s visitations. | parish buildings | General DAC policy statement, specific statement on heating | what flexibility do dioceses have to modify QI specs? As we pay for them, presumably we can, so let's do that.; And visitations and APCM is the archdeacons, I think | Revise general DAC environment policy in the light of NZC; new policy(s) on heating, including Env Net Gain when there is a negative or like-for-like replacement; policy on calculating pay back times for embodied carbon in PV; guidance on SoN and NZC; develop checklists for use in NZC compliance; emphasise 'due regard' - see if this can attract a data gathering component // APCM lies with others // QI raised at QI day without protests; develop new guidance with help of Nigel Walter // As' Visitations lies with others, but could usefully negotiate |  |  |  |  | 10 | 5
4.1 Dioceses | Every diocese should consider: | 7. Identifying required policy changes/levers for change: Create a DAC policy, set expectations for APCM reports, quinquennial inspections and archdeacon’s visitations. | parishes gen | For Buildings Department |  | 1) no advice will be given over APCM reports 2) visitations are not currently taking place 3) Ads Articles of Enquiry must be used sparingly // 4) set up a Bishop's Award scheme for individuals and parishes to celebrate achievements, including a Cathedral event. 5) perhaps encourage Dearnery Development Plans at their next iteration to consider NZC and Environment 6) engage with new Dpty Dir of Planning and the development of the next diocesan Strategic Plan for 2035 | [5 empty] | 5 | 5
4.1.1.08
4.1 Dioceses | Every diocese should consider: | 8. Instigating discussions with local authorities about proposed low carbon heat networks over the coming decade and the potential for any buildings across the Church estate to be connected to them. Feed the results of these discussions into the Net Zero Carbon Action Plan and specific building heating replacement plans. | strategy |  | 1) contact LAs to ask this |  |  | 2027 |  | NZC 1d | 1
|  | 4.1.1.09 | [8 empty] | 2
4.1 Dioceses | Every diocese should consider: | 9. Working with your HR department to ensure that your response to the climate crisis and the 2030 net zero carbon ambition is reflected in staff job descriptions, staff training (such as Carbon Literacy training), departmental plans and Key Performance Indicators. | central |  | The contracts will be updated when move to new office, so this is a chance to include this. Heads of Departments will include NZC in their KPIs. 2) ask the diocese's two HR consultants if they have a training package | [21 empty] | Sheena Bridgeman
4.1.1.10
4.1 Dioceses | Every diocese should consider: | 10. Promoting Eco Church and use the criteria to inform your planning. (see Milestones 4.2.9, 4.5.5 and 4.6.1). | parishes gen | see above | [6 empty] | 3 | 3
4.1 Dioceses | Every diocese should consider: | 10. Promoting Eco Church and use the criteria to inform your planning. (see Milestones 4.2.9, 4.5.5 and 4.6.1). | strategy |  | 1) DEO to cross check to use criteria to inform planning
4.2.0.04
4.2 Churches | Milestone | 4.2.4. Cathedrals and Churches: Over the duration of a Quinquennium and from 2022, all cathedrals and the top 20% of energy-consuming churches to develop net zero carbon action plans for completion by no later than 2027. These should include, as a minimum, low-carbon heating options to replace fossil-fuel heating at end-of-life, such as heat pumps or far infra-red heating panels. The Action Plan should also contain a Heating Resilience Plan which should consider how to manage heat should the existing system fail, to avoid needing a quick like-for-like fossil-fuel replacement. | parish buildings | Can we guestimate the top 20% from the REACH data? Yes, I think we can - will need a bit of cleaning up and hole filling. Do we need to provide a template plan for these parishes, or does such already existing on the NZC hub? | What data do you have on churches? You did a survey that included heating etc, might you send me the spreadsheet of the results? Is there a spreadsheet from REACH Ely? Did Kylie ever write up her work?; I am not worried over the exaxt 20%, so long as we engage eventually with a fifth. However, for the full fifth I would be happy to delay until we have coped with engaging with about 15-20 churches 'now'. | Use REACH Ely data (from 240 churches) to identify 'key churches' that may be high C-emitters or, at least, to be large and busy (we can learn how they are low emitters if that is the case) // develop a support package for these 20% churches // promote Heat Decarb Plans and Heat Resilience Plans // undertake audits of 10 churches at estimated £1k each | 2022-27 | 2025 |  | NZC 10d | 20 |  |  |  | 10000
4.2 Churches | Milestone | 4.2.4. Cathedrals and Churches: Over the duration of a Quinquennium and from 2022, all cathedrals and the top 20% of energy-consuming churches to develop net zero carbon action plans for completion by no later than 2027. These should include, as a minimum, low-carbon heating options to replace fossil-fuel heating at end-of-life, such as heat pumps or far infra-red heating panels. The Action Plan should also contain a Heating Resilience Plan which should consider how to manage heat should the existing system fail, to avoid needing a quick like-for-like fossil-fuel replacement. | parishes gen | Geoffrey / Buildings Department to lead on. | work for better information flow between buildings, M&M and Comms | Buildings team will identify top 20% and communicate directly with them. // helpful, though, if general parish comms mentions this
4.2.0.5
4.2 Churches | Milestone | 4.2.5. Dioceses: Every diocese has a 90%+ completion rate for the Energy Footprint Tool, and 100% of cathedrals complete the Energy Footprint Tool. | parishes gen | Crucial for base line figures. Filling in the EFT is very easy - need ot make it as easy as possible for parishes. | Email to wardens in May of each year. Ensure it makes clear purpose + how easy the process is. | 1) NC to check ease of completion - esp can it be done at benefice level with one login? Can it be done by treasurers without clergy/wardens present to fill in the mission Qs? 2) delay promotion until 2024 to be fully prepared 3) ask if can present to meeting of deanery finance chairs (via Brian Atling) 4) prepare video for use at deanery and parish level 5) ask the 2 Cambridge deaneries to help with their experience 6) email and other digital comms LINK all this in with comms strategy // Prepare training/promotion video next year to show todeanery meetings of treasurers, perhaps with option of live video link for qeuestions. Also raise at diocesan meeting for deanery treasurers, assuming this happens | 2023+ |  |  |  | 5
4.2.0.09
4.2 Churches | Milestone | • All dioceses reach Gold Eco Dioceses standard – targets are currently being amended by A Rocha. | strategy | Register its intent. // Appoint an individual or group to coordinate progress. // Write an environmental policy. // Have a certain percentage of churches in the Diocese registered and awarded Eco Church status. [Bronze Eco Diocese: 10% of local churches registered; 5% of local churches awarded // Silver Eco Diocese: 40% of local churches registered 30% of local churches awarded of which at least a third of these awards should be Silver or higher] // Achieve Eco Church status for its Diocesan House or Office. // Embed environmental issues into its ministerial education. // Manage Diocesan investments ethically. // Work collaboratively with other Dioceses and faith groups. // Establish a habit of recording and celebrating environmental achievements. // | done // GH is the appointed person - should this change to the DEO? // 1) write Env Policy and get approved by synod // see parishes tab // 2) get diocesan central engaged on this // 3) get M&M engaged with this // do we not do this now? // the regional collaboration should tick this box, but I have also just asked my friend who is the regional minister for Cambs for the Baptists about it // 3+) get M&M engaged here too |  | 2029 | 2024 Q2 for actions // Bronze by 2027 |  |  | 2 | 3 | 5
4.2 Churches | Milestone | 4.2.9 • 10% of local churches in every diocese registered; 5% of local churches awarded at least at bronze (= Bronze Eco Dioceses standard). | parishes gen | Top priority to get churches involved in Eco Church Awards. Take up in this Diocese is very low to date. | Letter from Bishop in Creationtide. Also push on Ministry Mailings (but this is not enough itself). Also to ensure that we are communicating and profiling best practice examples from within the diocese to encourage some aspirational thinking. | 1) Ask GH to raise this at churchwardens day 16 Sept 2) engage keen churches as mentors (St Paul's Hills R, Over); video 3) develop integration of Network Lunches with EcoCh churches (club idea and self-help groups) // 4) develop a Creationtide momentum with 5) messaging LINK all this in with Comms strategy, 6) schools enagement, 7) data collection (EFT etc) (too late for this year, but do next spring) [engage with some EcoChurches to see if they can help promote, e.g. video of what they have done and how they have gone about it.] | 2023 |  |  | DEO 5d; Bps Advs 5d |  | 5 | 5
4.2 Churches | Milestone | • 40% of local churches registered; 30% of local churches awarded, of which at least a third of these awards should be Silver or higher (= Silver Eco Dioceses standard). | parishes gen |  | Start up monthyl eco-mailing or ensure that it is integrated within the current communication avenues | Link EcoChurches into the Network Linch Hubs being organised by the Bps Climate Advisers - see above | 2026
4.2.0.10
4.2 Churches | Milestone | 4.2.10 At the point of contract renewal, switch to 100% green electricity tariff, encouraged through a major national switching campaign | parish buildings |  |  | This is a comms strategy mainly under parishes general tab | 2024
4.2 Churches | Milestone | 2.2.10 At the point of contract renewal, switch to 100% green electricity tariff, encouraged through a major national switching campaign | parishes gen |  | Contact all treasurers to push this. Work with the buildings and finance team to profile exmaples | 1) contact Treasurers to encourage this - link in with EFT messaging; give clarity over comparative prices of the Parish Buying scheme | 2024 |  |  | as part of 4.2.5
4.2.0.11
4.2 Churches | Milestone | 2.2.11 Having reviewed options to replace fossil fuels, all churches and cathedrals that remain with gas heating, switch to a ‘green’ gas tariff at the point of contract renewal20, based on national advice about the criteria to apply. | parishes gen |  | Contact all treasurers to push this. Ensure that we are communicating well the national guidance through the various comms channels | 1) we shall not promote this at this time because of its cost and debatable green credentials | 2024 |  |  | 0
4.2 Churches | Milestone | 4.2.11 Having reviewed options to replace fossil fuels, all churches and cathedrals that remain with gas heating, switch to a ‘green’ gas tariff at the point of contract renewal20, based on national advice about the criteria to apply. | parish buildings |  |  | ditto, but is it worth their money? | 2024
4.2.0.12
4.2 Churches | Milestone | 2.2.12 No new oil boilers installed in churches and cathedrals after this date. [contingent on government action to connect rural communities to the grid.] | parishes gen |  | leave this for Buildings team as and when a case arises | comms will need to include message about new Fac Rules | 2025
4.2 Churches | Milestone | 4.2.12 No new oil boilers installed in churches and cathedrals after this date. [contingent on government action to connect rural communities to the grid.] | parish buildings |  |  | this should be emphasised by DAC heating policy and communicated // however, many remote churches will not have gas available; three phase electricity may be expensive to obtain the upgraded supply | 2025 | 2023 for policy
4.2.0.13
4.2 Churches | Milestone | 2.2.13 All churches to have energy efficient lighting installed throughout, with timers and light and motion sensors where appropriate. | parishes gen | For Buildings Department.Advice needed on contractors, as finding people for this work can be hard. If scaffolding is needed this is expensive. | Work with th buildings team to ensure that best practice examples are communicated well | 1) double message: if it is easy to swap bulbs for LEDs, then really no excuse; if challenging, then refer to Buildings team | 2025
4.2 Churches | Milestone | 4.2.13 All churches to have energy efficient lighting installed throughout, with timers and light and motion sensors where appropriate. | parish buildings |  |  | The DAC lighting policy needs to include this nd then be communicated | 2025 | 2024 for policy |  | NZC 1d | 1
4.2.0.14
4.2 Churches | Milestone | 2.2.14 at least the top 20% of energy-consuming churches, to deliver the actions in their Net Zero Carbon Action Plans. | parishes gen | For Buildings Department |  |  | 2030 |  |  |  | 5
4.2 Churches | Milestone | 4.2.14 at least the top 20% of energy-consuming churches, to deliver the actions in their Net Zero Carbon Action Plans. | parish buildings |  |  | this is not really a separate milestone from 4.2.4 | 2030
4.2.2.1
4.2 Churches | Every church should consider: | 1. Creating a Net Zero Carbon Action Plan, including a Heat Decarbonisation Plan, using the national guidance, as set out in the milestones above. | parish buildings |  |  | see above
4.2 Churches | Every church should consider: | 1. Creating a Net Zero Carbon Action Plan, including a Heat Decarbonisation Plan, using the national guidance, as set out in the milestones above. | parishes gen |  | 4.2.4. Cathedrals and Churches: Over the duration of a Quinquennium and from 2022, all cathedrals and the top 20% of energy-consuming churches to develop net zero carbon action plans for completion by no later than 2027. These should include, as a minimum, low-carbon heating options to replace fossil-fuel heating at end-of-life, such as heat pumps or far infra-red heating panels. The Action Plan should also contain a Heating Resilience Plan which should consider how to manage heat should the existing system fail, to avoid needing a quick like-for-like fossil-fuel replacement.
4.2.2.2
4.2 Churches | Higher energy using churches should consider: | 2. They should actively plan and fundraise to implement their Net Zero Carbon Action Plan. | parishes gen |  |  | include in general comms
4.2.1.1
4.2 Churches | Every church should consider: | 1. Passing a motion at your PCC or equivalent, to recognise the climate emergency, and the General Synod target of 2030. Make a commitment as a church. | parishes gen |  |  | Will not encourage PCCs to do this 1) will ask deaneries if they would welcome a presentation on NZC 2) try to organise deanery programmes of visiting keen parishes and ending by speaking to synods (look to any deaneries who have identified environment in their development planning) [suggest a draft motion?] |  |  |  | 15 deaneries; DEO 7d | 7 | 7
4.2.1.2
4.2 Churches | Every church should consider: | 2. Measuring your carbon footprint with the Energy Footprint Tool. Report the results through your APCM or equivalent. | parishes gen
4.2.1.3
4.2 Churches | Every church should consider: | 3. Using the Practical Path to Net Zero Carbon as a start point for an action plan. | parishes gen |  |  | include promoting PPNZC in comms
4.2 Churches | Every church should consider: | 3. Using the Practical Path to Net Zero Carbon as a start point for an action plan. | parish buildings | GH already has a presentation on the practical path. The maintenance and gutters station will be supported by the gutter scheme. | Might you share the ppt? Can you tell me more about the gutter scheme?; for my talk to architects next week, can you direct me to the current QI instructions, pay rates etc? | Work on how to promote PPNZC with Comms and Parish General; esp around maintenance // develop and promote gutter scheme (can these be adapted to a tree inspection scheme?) // consider other elements of PPNZC |  |  |  | DEO 2d; NZC 2d | 2
4.2.1.4
4.2 Churches | Every church should consider: | 4. For most smaller churches, heated only a few hours per week or month, the carbon footprint is already very low. Here, good maintenance is key: looking after the roof, gutters, windows, and doors, and tackling the causes of damp. | parish buildings | Ditto above |  | Ashleigh X is v. keen on rerendering. Do our architect members have a view on this; Ground lowering now seems out of fashion; importance of drains; complaints against trees // issue of loss of pews, pew platforms, wooden panelling (are there modern materials that are even more efficient but also aesthetically pleasing?) // tackling draughts, eg ill-fitting windows (but bats) and doors (bats even more!) - maybe curtains - see next
4.2.1.5
4.2 Churches | Every church should consider: | 5. The most common recommendation from the audits is to switch to a green electricity tariff. As of Q2 2022 this is difficult due to turmoil in the energy markets. When this settles switching to green electricity is an affordable swap from standard ‘brown’ grid electricity. This is an easy win: the analysis of the first year of the Energy Footprint Tool suggests that churches could reduce their collective carbon footprint by 22% through this step alone. Combining electric heating with a 100% renewable tariff makes a church - nearly - net zero carbon, leaving only their transport to consider (see Section 5.3 for travel). | parishes gen |  |  | this can be part of the messaging over the switch to green elec [important info for us to include in comms]
4.2.1.6
4.2 Churches | Every church should consider: | 6. The second most common recommendation is on lighting (although a relatively small user of energy compared to heating). For light, the change required is often straightforward, with a shift to LED lamps powered by a 100% green electricity tariff, lighting becomes both energy efficient and net zero carbon. Movement and light-level sensors can be useful if lights are routinely left on. | parishes gen |  |  | this can be part of the messaging over the switch to LED bulbs [important info for us to include in comms]
4.2.1.7
4.2 Churches | Every church should consider: | 7. The most cost-effective option is to ’turn off’ lights and equipment that are not needed and review heating settings to reduce carbon emissions and save money on energy costs. | parishes gen |  |  | this can be part of a general energy message [heating settings v imp]
4.2.1.8
4.2 Churches | Every church should consider: | 8. Taking appropriate steps to reduce heat loss, and to make existing systems as efficient as possible. Plan ahead for replacements when the current system reaches the end of its working life by creating a Net Zero Carbon Action Plan, including a Heat Decarbonisation Plan, using the national guidance. | parishes gen
4.2 Churches | Every church should consider: | 8. Taking appropriate steps to reduce heat loss, and to make existing systems as efficient as possible. Plan ahead for replacements when the current system reaches the end of its working life by creating a Net Zero Carbon Action Plan, including a Heat Decarbonisation Plan, using the national guidance. | parish buildings | Can we identify issues with the way heating systems are currently used? Left on too long? Turned on too early? We don't really know. Remote timers as part of a Hive type system, can also be linked to security. | I think the emphasis should be on planning ahead with Heat Decarb plans and Heat resiilence plans | draught control (door curtains, inner lobbies, well-fitting windows - but then need ventilation!) // heating control systems key - well-designed but easy to operate; timing regimes; other issues? Remote control linked to security // promote Heat Decarb Plans AND Heat Resilience Plans
4.2.1.9
4.2 Churches | Every church should consider: | 9. Avoiding making a large intervention for a small energy saving; all the materials you use have an embodied carbon cost. | parish buildings | Noted, but embodied is out of scope isn't it? | out ofd scope, but should still be sonsidered as it might be large | Is it wise to keep old plant in so can be refurbished when new heating systems are developed? // DAC policy to expect some estimate of embodied C and payback times in larger projects of all types (not just those aiming for NZC)
4.2.3.1
4.2 Churches | Every diocese should consider | 1. Embed the Fifth Mark of Mission in the work of the DAC and create an environmental policy, appropriate for your diocese. | parish buildings |  |  | see above
4.2.3.2
4.2 Churches | Every diocese should consider | 2. Encourage uptake of the resources that exist, such as the Energy Footprint Tool, Practical Path to Net Zero Carbon, webinar programme, and heating guidance. | parishes gen | Knowledge of this guidance needs to expand - publicity required. | Media saturation during creationtide (alongside push to switch tarifs and joins Eco-Church) | Lobby national church team to make finding advice easier [The national church has provided almost too much info - but also has it scattered about rather and it can be difficult to find what you want.. Can we help with this - perhaps at regional level?] |  |  |  |  | 5
4.2 Churches | Every diocese should consider | 2. Encourage uptake of the resources that exist, such as the Energy Footprint Tool, Practical Path to Net Zero Carbon, webinar programme, and heating guidance. | M&M & Comms | Repeated and regulalr (monthly) reminders through usual comms channels on the tools availble to parishes and the benefits to the parishes utlising them. | Activities should be scheduled through internal comms channels throughout the year. Comms messaging will be determined by the focus of the NCZ plan and the messaging around supporting that. | 1) NZC team to lobby national church for more accessible routes into their resources 2) NZC team to produce a simple guide into resources for diocesan website and elsewhere
4.2.3.3
4.2 Churches | Every diocese should consider | 3. During visitations, Archdeacons to ask churches about using the Energy Footprint Tool, using the Practical Path to Net Zero to create an action plan, and about planning ahead for replacing their oil and gas heating. | M&M & Comms | This should sit with the wider Deanery planning process and should form a component part of a deaneries plan through that process. | Activities should be scheduled through internal comms channels throughout the year. Comms messaging will be determined by the focus of the NCZ plan and the messaging around supporting that. | 1) NZC team to include messages about PPNZ, heating plans and heating resilience plans in their messaging.
4.2 Churches | Every diocese should consider | 3. During visitations, Archdeacons to ask churches about using the Energy Footprint Tool, using the Practical Path to Net Zero to create an action plan, and about planning ahead for replacing their oil and gas heating. | parishes gen | visitations not currently taking place
4.2.3.4
4.2 Churches | Every diocese should consider | 4. Carry out a skills audit of your DAC and recruit new advisors where needed (supported by the national process – milestone 5.2.3). | parish buildings | We porbably need someone who's good with green technologies of all types. | It is not just heat, it is an allround interest in sustainable building. The right architect might be best | skills needed are not just heating engineer; also need lighting, elec generation, A/V schemes (? are these really big users of power across the week; if they are using renewable elec prob ok), general sustainable architecture (including around partitioning for heat control) // set up a NZC vetting group with these specialists to say if can tick the env box: architect, M&E, theology etc |  |  |  |  | 2
4.2.3.5
4.2 Churches | Every diocese should consider | 5. Identify your 20% of largest, busiest churches, and – to the degree capacity allows - proactively seek ways to support them, to plan for and achieve net zero carbon. | parish buildings | Is it assumed here that largest and busiest = highest users of carbon, or is this a different 20% for a different reason? |  | also see earlier // it is not just 'high' users, but inefficient users who could change. Hard to identify the most relevant. Use a scoring system to pick out medium users. High but busy and efficient users may have something to teach us. // want to identify case studies such as those who have gone all electric recently - what is their experience like? // I think we need to offer site visits, prob a series: intial to raise enthusiasm and start planning process, second to support planning, third to put plans into action in sourcing technical expertise both consultant and contractor; perhaps we can organise 'deanery' visits to minimise travel (both time and fuel) |  |  |  |  | 10
4.2.3.6
4.2 Churches | Every diocese should consider | 6. Seek a firm who will carry out a free desk-top analysis of the churches most suitable for solar panels, and potentially EV car charging. | parish buildings | GH has been in discussions with eBound who may be looking at moving in this direction. |  | GH has been in discussions with eBound who may be looking at moving in this direction.
4.3.0.3
4.3 Schools | Milestone | 4.3.3 • Dioceses to identify schools with boilers approaching end-of-life, and support schools through funding feasibility to identify opportunities for a more sustainable solution and apply for grant funding from BEIS to deliver those by 2023 | VA schools | Instigating whether we are eligible. | 1) eithere ask schools what they know of their boilers | we need to know this in order to identify which schools need a heat resilience plan pronto | 2023 | 2024 |  | can be covered within existing resources |  |  | 6 | [13 empty] | Jacqueline McCamphill | Diocesan Board of Education
4.3 Schools | Milestone | • revise to include Execution Plans (funding, delivery method, programme etc) by 2024 | VA schools | Planning year currently - implementation will commence from April 2024 through to 2025 (but subject to 10% financial contribution challenge being overcome) |  | I imagine execution plans are actually developed by the schools, but if by the diocese, some sort of delivery plan is needed for each school, I think | 2024 | 2026 |  | can be covered within existing resources | [16 empty] | Jacqueline McCamphill | Diocesan Board of Education
4.3 Schools | Milestone | • revise to include Heat Decarbonisation Plan (HDP) by 2026 | VA schools | Assessment per school would require to be done as this would not be identified through the individual school condition surveys. The 6 schools identified through SALIX would incorporate measures around decarbonisation. The challenge is funding. | 1) execution plans for all schools, with heat decarbonisation plan and heat resilience plan incorporated in all cases | The big challenge is funding, but have the condition surveys led to execution plans - ready to roll if funding becomes available? Can schools plan ahead to save for the 10% // use NZCA to release staff time | 2026 | 2026 |  |  |  |  | 20 | [13 empty] | Jacqueline McCamphill | Diocesan Board of Education
4.3 Schools | Milestone | • deliver the actions in these plans (subject to funding). | VA schools | As above. |  |  | 2030 | 2030 | [19 empty] | Diocesan Board of Education
4.3 Schools | Milestone | 4.3.3 • Dioceses to identify schools with boilers approaching end-of-life, and support schools through funding feasibility to identify opportunities for a more sustainable solution and apply for grant funding from BEIS to deliver those by 2023 | DMAT | Boilers that require replacement can be considered for alternatives but it is not just the boiler that will need consideration but the plant-room and associated equipment as well as the heat delivery into the buiding - radiators et. all may need upgrading. An effective way of reducing carbon emmissions is to use less of any type of fuel by insulating / upgrading the building fabric. There does not appear to be any stand-alone funding for this. |  |  | 2023
4.3 Schools | Milestone | • revise to include Execution Plans (funding, delivery method, programme etc) by 2024 | DMAT |  |  |  | 2024
4.3 Schools | Milestone | • revise to include Heat Decarbonisation Plan (HDP) by 2026 | DMAT |  |  |  | 2026
4.3 Schools | Milestone | • deliver the actions in these plans (subject to funding). | DMAT |  |  |  | 2030
4.3.0.4
4.3 Schools | Milestone | 4.3.4. DBE: DBE to take the lead in the promotion of the Energy Toolkit in their schools to commence data collection from utility bills. | VA schools | We need sight of the energy toolkit in order to assess this requirement. It would be positive to get each school engage and monitor their usage. (once a quarter). They would then bring that into their GEMS package. | 1) design a comms package to promote the EFT to schools 2) start to use the data to identify schools with the highest carbon emissions | The link for the toolkit is at https://eft.parishreturns.info/, but do look at the home page https://www.churchofengland.org/about/environment-and-climate-change/about-our-environment-programme/energy-toolkit and the many other resources around that page. I shall attach a list of the schools in the database at present for you to check they are all there. So far, none have entered their data. This is an annual system, not quarterly, though // can you tell me what GEMS is? | 2022+ | 2024 |  | can be covered within existing resources | [16 empty] | Jacqueline McCamphill | Diocesan Board of Education
4.3 Schools | Milestone | 4.3.4. DBE: DBE to take the lead in the promotion of the Energy Toolkit in their schools to commence data collection from utility bills. | DMAT | Data collection from energy bills is a useful and real-time tool to identify where and what type of energy use is highest. This can help target reduction in energy use and carbon reduction. |  |  | 2022+
4.3.0.5
4.3.0.6
4.3 Schools | Milestone | 4.3.6. DBE: DBE to take the lead in the promotion of smart meter installations in schools and be undertaking data analysis from the information provided. | VA schools | This is not an improvement (not improving condition) therefore would not meet the SCA criteria - further information and consideration is required. |  | part of the comms package | 2023+ |  |  |  | 2 | [15 empty] | Jacqueline McCamphill | Diocesan Board of Education
4.3 Schools | Milestone | 4.3.6. DBE: DBE to take the lead in the promotion of smart meter installations in schools and be undertaking data analysis from the information provided. | DMAT | Smart meters can highlight for example periods of time when the school is closed but when energy consumption is still high so that schools can act to reduce energy use. |  |  | 2023+
4.3.0.7
4.3 Schools | Milestone | 4.3.7. Schools: All schools to work with their procurement provider to switch to green energy tariffs at point of contract renewal*. Having reviewed options to replace fossil fuels, any school remaining on gas heating should switch to a ‘green’ gas tariff, based on national advice about the criteria to apply. | VA schools | The Diocese do not have any remit and power to enforce this requirement as it would be a school decision, supported by the LA. The Diocese would encourage this type of initiative providing the school could afford to do so with a reputable provider The challenge is the schools will decide based on what is a cheaper option so will only happen if viable. | 1) design a comms package ( including promoting promote the EFT) to schools | We are working on a diocesan AP, so we cannot commit schools themselves, of course. But, how are the schools to know of the national Routemap and these milestones and points to consider? That is our task. | 2025 | 2024 |  | can be covered within existing resources | 2 | [15 empty] | Jacqueline McCamphill | Diocesan Board of Education
4.3 Schools | Milestone | 4.3.7. Schools: All schools to work with their procurement provider to switch to green energy tariffs at point of contract renewal*. Having reviewed options to replace fossil fuels, any school remaining on gas heating should switch to a ‘green’ gas tariff, based on national advice about the criteria to apply. | DMAT | It is challenging to understand how 'green' electricity is separated from 'non-green' electricity when it is all delivered through the same network....similarly with 'green' gas. There are schools on oil-fired boilers which are unable to change to another fuel type due to location / physical space. |  |  | 2025
4.3 Schools | Every DBE should consider: | 1. Once schools understand how they are performing they need to be able to identify what the technical route is to achieve net zero carbon. The best way of doing this is to a Capital Asset and Climate Action Plan (referred to in other parts of this document as a Net Zero Carbon Action Plan) containing a Heat Decarbonisation Plan (HDP). The key to progressing schools towards the target is for them to find a bespoke route by commissioning these audits and establishing business cases to bid for funding required to deliver the projects that are identified. Without this information, and an appreciation of the technical solutions, progress may be halted. | VA schools | What is your tariff. Age of the boiler and determine the timing of the renewal. DO you have LED lighting. | 1) conduct initial audit and development of a NZC AP for three sample schools 2) use this experience to guide other schools on how to do this | Your questionns would be a good start |  | 2025 |  | can be covered within existing resources | 3
4.3 Schools | Every DBE should consider: | 1. Once schools understand how they are performing they need to be able to identify what the technical route is to achieve net zero carbon. The best way of doing this is to a Capital Asset and Climate Action Plan (referred to in other parts of this document as a Net Zero Carbon Action Plan) containing a Heat Decarbonisation Plan (HDP). The key to progressing schools towards the target is for them to find a bespoke route by commissioning these audits and establishing business cases to bid for funding required to deliver the projects that are identified. Without this information, and an appreciation of the technical solutions, progress may be halted. | DMAT | I repeat the necessity of having an experienced, technically-knowledgeable and independent assessor who can identify practical solutions as every school building is different, has different heat losses, fabric and requirements. The building use patterns are very different from domestic houses and heat-pumps (for example) need very specific consideration to be able to deliver the real heating requirements for a school however convincing the arguement is from those in the business of supplying this equipment.
4.3.1.2
4.3 Schools | Every DBE should consider: | 2. Reviewing the Wayfinders Project5 schools reports, available on the Net Zero Carbon Resource Hub, as a starting point. | VA schools | Diocese to review the report, as stated, to determine relevance. |  | I have forgotten how to login to this. The administrator is on hols at present.
4.3.1.3
4.3 Schools | Every DBE should consider: | 3. Dioceses are encouraged to support the allocation of a significant proportion of the capital funding received, including capital funding for Boards of MATs (CIF or SCA as above), to fund projects outlined in HDPs. This would demonstrate progress against the HDP. Other capital works such as solar panels and LED lights could also be funded through school capital (through SCA). The significant barrier is the cost of the actual heat decarbonisation, for example, moving from fossil gas/oil to air-source or ground-source heat pump (especially as this may cost perhaps 3 or 4 time more than a gas replacement, although running costs may be lower). Where sustainable technology is comparatively expensive, it becomes difficult to justify and prioritise the limited sum of school capital funding available. These are issues that will have to continue to be addressed collectively as we progress towards 2030. There are some proposals for funding in the DfE draft Sustainability and Climate Change Strategy along with evaluation of best value for money approaches for retrofitting education buildings and developing retrofit and repair standards. | VA schools | All VA schools have been assessed for Salix funding to move away from fossil fuels. Out of 16 VA schools only six were identified as having a business case and funding has been secured subject to the Diocese agreeing to make their contribution and potentially assisting schools with their 10% mandatory contribution. Other capital works like the replacement to LED lighting are being promoted where possible. Each school must confirm how their recent direct funding from the government for energy improvement works have been allocated. | 1) review school reports on their use of direct funding to understand how these are working and to spread good practice 2) DBE and MAT to discuss how to support this allocation |  |  |  |  | can be covered within existing resources
4.3 Schools | Every DBE should consider: | 3. Dioceses are encouraged to support the allocation of a significant proportion of the capital funding received, including capital funding for Boards of MATs (CIF or SCA as above), to fund projects outlined in HDPs. This would demonstrate progress against the HDP. Other capital works such as solar panels and LED lights could also be funded through school capital (through SCA). The significant barrier is the cost of the actual heat decarbonisation, for example, moving from fossil gas/oil to air-source or ground-source heat pump (especially as this may cost perhaps 3 or 4 time more than a gas replacement, although running costs may be lower). Where sustainable technology is comparatively expensive, it becomes difficult to justify and prioritise the limited sum of school capital funding available. These are issues that will have to continue to be addressed collectively as we progress towards 2030. There are some proposals for funding in the DfE draft Sustainability and Climate Change Strategy along with evaluation of best value for money approaches for retrofitting education buildings and developing retrofit and repair standards. | DMAT | Due to the present condition of schools and lack of adequate maintenance over a sustained period of time, it is unlikely that a significant amount fo funding can be freed up for the delivery of net zero unless a substantial increase in capital funding becomes available. It is necessary to upgrade fabric alongside any renewable heat sources in order for them to be effective. The idea that running costs are lower for 'green ' energies such as air-source heat pumps is not true. It is not only the switch to decarbonisation but the whole-life running costs i.e. replacement of units (often not as long-lived as more traditional types, and has this been calculated into the real carbon-reduction figures?
4.3.1.4
4.3 Schools | Every DBE should consider: | 4. Some local authorities, who have responsibility for school places, have resolved to build greener and more efficient school buildings. Dioceses should support this policy and there should be an understanding that all new buildings – whether funded through PSPB, SCA or Basic Need or any other means – would have to have a non-carbon heat source and in effect be a net zero carbon building, as proposed in the DfE draft Sustainability and Climate Change Strategy for all new school buildings to be net zero carbon in operation by 2023. | VA schools | Diocese to determine how such an approach can be supported.
4.3 Schools | Every DBE should consider: | 4. Some local authorities, who have responsibility for school places, have resolved to build greener and more efficient school buildings. Dioceses should support this policy and there should be an understanding that all new buildings – whether funded through PSPB, SCA or Basic Need or any other means – would have to have a non-carbon heat source and in effect be a net zero carbon building, as proposed in the DfE draft Sustainability and Climate Change Strategy for all new school buildings to be net zero carbon in operation by 2023. | DMAT | This is the most cost-effective way to ensure an efficient building however the design and construction phases must be carefully considered which has NOT happened in recent newly-built schools, with both new school we have not having zoning for underfloor heating, meaning that the entire school heating has to be run for a small section of the building open over holidays.
4.3.1.5
4.3 Schools | Every DBE should consider: | 5. Dioceses should also consider the use of well-established diocesan landholdings and woodland as an asset not only in terms of offsetting for the diocese but also for use as forest schools and activities that raise awareness and appreciation of the natural environment. | VA schools | Noted and should be considered for offset purposes where net zero cannot be achieved. To be considered as an integral part of Diocesan wide strategy. | 1) collaborate with the diocesan Assets team to work at this. | they already have this as a task in their NZC AP |  |  |  | can be covered within existing resources
4.3 Schools | Every DBE should consider: | 5. Dioceses should also consider the use of well-established diocesan landholdings and woodland as an asset not only in terms of offsetting for the diocese but also for use as forest schools and activities that raise awareness and appreciation of the natural environment. | glebe | Relevant - We have looked at establishment possibly central resource to make available to all aspects of the Diocese, inc schools. See above for comments re carbon sequestration | Establishment of plan for central resource | This reminds me of Wilbraham. Are there other areas close to settlements which might be play areas and which might, instead, become more formalised as forest schools, either as official FSs or as well-used and maintained teaching resources by a local primary school or nursery? |  | 2030+ |  | Within normal portfolio planning process |  | 2 | [14 empty] | Glebe Officer | Assets Sub committee
4.3 Schools | Every DBE should consider: | 5. Dioceses should also consider the use of well-established diocesan landholdings and woodland as an asset not only in terms of offsetting for the diocese but also for use as forest schools and activities that raise awareness and appreciation of the natural environment. | DMAT | There are opportunities here to maximise the benefits of these assets.
4.3.1.6
4.3 Schools | Every DBE should consider: | 6. Regional Environment Groups can work with schools to identify opportunities to decarbonise from the data collected by the EFT. | VA schools | Noted, Diocese to establish a list of such groups to form partnerships, where possible, and promote to all schools. | 1) enquire about progress on these groups with national team and within the 5 Eastern Dioceses group | this is my job |  | 2023 |  |  |  | 2
4.3 Schools | Every DBE should consider: | 6. Regional Environment Groups can work with schools to identify opportunities to decarbonise from the data collected by the EFT. | DMAT | Agreed
4.3.1.7
4.3 Schools | Every DBE should consider: | 7. Regional Environment Groups can look at batching applications for funding where possible. | VA schools | Noted, refer to comment above
4.3 Schools | Every DBE should consider: | 7. Regional Environment Groups can look at batching applications for funding where possible. | DMAT | Must be based on well-designed schemes that will deliver the practical needs for schools
4.3 Schools | Every DBE should consider: | 8. Project delivery can be overseen by Regional Environment Groups and reported to the Diocesan EWG. | VA schools | Noted, refer to comment above
4.3 Schools | Every DBE should consider: | 8. Project delivery can be overseen by Regional Environment Groups and reported to the Diocesan EWG. | DMAT | Again, needs those who are technically experienced and independent in this specialist field.
4.3.1.9
4.3 Schools | Every DBE should consider: | 9. Regional Environment Groups can keep up to date with government thinking on skills, funding and technologies. | VA schools | Noted, refer to comment above
4.3 Schools | Every DBE should consider: | 9. Regional Environment Groups can keep up to date with government thinking on skills, funding and technologies. | DMAT | Agreed
4.3.2.1
4.3 Schools | Every school should consider: | 1. Supporting school governing boards to make a formal declaration (for example, Let’s Go Zero) to become net carbon zero by 2030 and encourage ex-officio governors to share good practices across the school and church community on this issue. | VA schools | Requires financial commitment and long term planning - should be considered as part of each school's GEM's property plan. | 1) encourage governing bodies to take these steps | I think this is much less about buildings and much more about people and so it doesn't need much funding. You may be assisted in this task by Mission and Ministry school mission officer and/or the DEO and bishop's advisers on climate, but your team will need to take the lead, perhaps it is you as the governance adviser? |  | 2024 |  | can be covered within existing resources |  | 4
4.3 Schools | Every school should consider: | 1. Supporting school governing boards to make a formal declaration (for example, Let’s Go Zero) to become net carbon zero by 2030 and encourage ex-officio governors to share good practices across the school and church community on this issue. | DMAT | How buildings are used and what users can do individually is essential and large part of reducing carbon emmissions.
4.3.2.2
4.3 Schools | Every school should consider: | 2. Establishing an ‘eco charter’ for school councils to implement, identifying personal pledges to work towards the target as a collective. | VA schools | To be developed as part of Diocesan wide strategy. | 1) ask national team for 'eco charters' that teachers could encourage school councils to adopt | [6 empty] | 1
4.3 Schools | Every school should consider: | 2. Establishing an ‘eco charter’ for school councils to implement, identifying personal pledges to work towards the target as a collective. | DMAT | How buildings are used and what users can do individually is essential and large part of reducing carbon emmissions. Pupils are very good at monitoring this.
4.3.2.3
4.3 Schools | Every school should consider: | 3. Providing an ‘Annual Resilience Statement’ to review their declaration. A suggestion is that this would be a statement setting out how directors/ governors are measuring the school’s climate resilience and targets, and addressing challenges over the short, medium and long term, including risks posed by climate change (as per the DfE draft Sustainability & Climate Change Strategy). Future planning and decision making should also be taken with consideration of any impact on future generations. | VA schools | Each school would be reliant environment groups to provide free guidance as they may not be able to afford to pay for a consultant to guide them. | 1) work with governing bodies to encourage them to do this | a super-duper one would need that help, but I think what is in mind is to get governors to actually think about these things themselves. There may be a national model schools can use. |  |  |  | can be covered within existing resources
4.3 Schools | Every school should consider: | 3. Providing an ‘Annual Resilience Statement’ to review their declaration. A suggestion is that this would be a statement setting out how directors/ governors are measuring the school’s climate resilience and targets, and addressing challenges over the short, medium and long term, including risks posed by climate change (as per the DfE draft Sustainability & Climate Change Strategy). Future planning and decision making should also be taken with consideration of any impact on future generations. | DMAT | This is possible, but should not cause undue anxiety to pupils. Future planning should always take account of the whole life of the building.
4.3.2.4
4.3 Schools | Every school should consider: | 4. Switching to 100% ‘green’ energy tariffs through their procurement providers. Switching to renewable tariffs is an easy way for schools to reduce reliance on fossil fuels, and they can be encouraged to switch as soon as possible, while recognising that some are tied-in to local authority energy tariffs for a number of years. | VA schools | Such an approach may impose a more expensive energy tariff and therefore may not be financially viable for a school already working to a tight budget unless the Diocese are prepared to subsidise. Could the Diocese approach a single energy provider to include all schools to negotiate an acceptable tariff rate as a means to reduce costs? | 1) investigate a bulk provider | Can schools use the Parish Buying system? They have a nationally negotiated rate for green electricity |  |  |  | can be covered within existing resources | 2
4.3 Schools | Every school should consider: | 4. Switching to 100% ‘green’ energy tariffs through their procurement providers. Switching to renewable tariffs is an easy way for schools to reduce reliance on fossil fuels, and they can be encouraged to switch as soon as possible, while recognising that some are tied-in to local authority energy tariffs for a number of years. | DMAT | Again - it is challenging to understand how 'green' electricity is separated from 'non-green' electricity when it is all delivered through the same network....similarly with 'green' gas. There are schools on oil-fired boilers which are unable to change to another fuel type due to location / physical space.
4.3.2.5
4.3 Schools | Every school should consider: | 5. The Capital Asset Management Plan and Climate Action Plan, both containing Heat Decarbonisation Plans (HDPs), provide a roadmap toward the net zero carbon target through retrofitting buildings. From these plans, a phased plan for implementing the HDP can be developed at a strategic level with Boards of Education. A significant amount of the capital works required to meet the HDP will be fabric work (to roofs and windows) which can be funded through school capital funding (funding routes include through CIF and SCA, although CIF is unlikely to provide support for decarbonisation projects directly without a significant contribution from the Academy). HDPs will also identify ‘low-hanging fruit’ and will discuss habits and working practices that could be addressed relatively easily. Reducing energy consumption is a key first step. | VA schools | We are finding that significant capital projects such as roofs etc are difficult to deliver because of the need for each school to contribute 10%, which they can't afford, so in reality they cannot afford more expensive projects even when SCA funding is available. | this is the biggie that faces all church schools. Can you ask the national team how they are now approaching this issue |  |  |  |  | can be covered within existing resources
4.3 Schools | Every school should consider: | 5. The Capital Asset Management Plan and Climate Action Plan, both containing Heat Decarbonisation Plans (HDPs), provide a roadmap toward the net zero carbon target through retrofitting buildings. From these plans, a phased plan for implementing the HDP can be developed at a strategic level with Boards of Education. A significant amount of the capital works required to meet the HDP will be fabric work (to roofs and windows) which can be funded through school capital funding (funding routes include through CIF and SCA, although CIF is unlikely to provide support for decarbonisation projects directly without a significant contribution from the Academy). HDPs will also identify ‘low-hanging fruit’ and will discuss habits and working practices that could be addressed relatively easily. Reducing energy consumption is a key first step. | DMAT | I agree that reducing energy consumption by improving how the buildings are used, upgrading controls, management, insulation, excluding drafts, installing double-glazing etc. are probably a much more realistic way of reducing carbon emmissions than trying to fit 'green technologies' such as heat pumps into a school building unless there is a significant uplift in capital funding.
4.3.2.6
4.3 Schools | Every school should consider: | 6. Integrating decarbonisation into estate strategy and planning in schools and increase efforts to ensure that schools work to set a sustainable strategy and vision for their estates. Integrating environmental considerations, an understanding of climate risks, and where adaptations are required, are key to driving change. The kinds of changes needed to school buildings include: | VA schools | Refer to my comment above regarding GEM's property plan.
4.3 Schools | Every school should consider: | • Upgrading thermal envelopes (where required) such as walls, windows, roofs, floors | VA schools | Refer to comment above regarding the 10% contribution.
4.3 Schools | Every school should consider: | • Upgrading thermal envelopes (where required) such as walls, windows, roofs, floors | DMAT | These are the priority as they usually address fabric issues as well.
4.3 Schools | Every school should consider: | • Focusing on big win/lower cost items first, such as roof insulation | VA schools | Refer to comment above regarding the 10% contribution.
4.3 Schools | Every school should consider: | • Focusing on big win/lower cost items first, such as roof insulation | DMAT | Agreed
4.3 Schools | Every school should consider: | • Installing energy efficient boilers and heating equipment powered by ‘green’ energy tariffs, OR | VA schools | Refer to comment above regarding the 10% contribution.
4.3 Schools | Every school should consider: | • Installing energy efficient boilers and heating equipment powered by ‘green’ energy tariffs, OR | DMAT | Agreed - see earlier caveats to this
4.3 Schools | Every school should consider: | • Installing low carbon heating systems (such as heat pumps or biomass) and/or renewable energy sources (wind, solar, etc) | VA schools | All VA schools have been assessed for Salix funding.
4.3 Schools | Every school should consider: | • Installing low carbon heating systems (such as heat pumps or biomass) and/or renewable energy sources (wind, solar, etc) | DMAT | Consideration should be given to the whole life costs of such installations - life expectancy of heat pumps etc.
4.3 Schools | Every school should consider: | • Switching to energy-efficient lighting and other building systems | VA schools | Such works are being promoted.
4.3 Schools | Every school should consider: | • Switching to energy-efficient lighting and other building systems | DMAT | Agreed - an effective way of energy reduction
4.3 Schools | Every school should consider: | 7. Assessing the school’s current approach and consumption of resources which will help to motivate sustainable practices – a requirement for Schools and DBEs that hold capital funding. Effective buildings maintenance, glazing, insulation and draughtproofing are all important to improving efficiency. | VA schools | Refer to comments above regarding GEM's property management plan.
4.3 Schools | Every school should consider: | 7. Assessing the school’s current approach and consumption of resources which will help to motivate sustainable practices – a requirement for Schools and DBEs that hold capital funding. Effective buildings maintenance, glazing, insulation and draughtproofing are all important to improving efficiency. | DMAT | Agreed
4.3.2.8
4.3 Schools | Every school should consider: | 8. Other improvements to energy efficiency; for example, through swapping to LED lighting, and to include provision for any planned installation of renewables on buildings such as solar PV. This also has the benefit of reducing energy demand and the possibility that schools may have to review incoming electricity supply. An example of a net zero carbon school can be found at St Andrews CofE Primary School. | VA schools | Refer to comments above regarding GEM's property management plan.
4.3 Schools | Every school should consider: | 8. Other improvements to energy efficiency; for example, through swapping to LED lighting, and to include provision for any planned installation of renewables on buildings such as solar PV. This also has the benefit of reducing energy demand and the possibility that schools may have to review incoming electricity supply. An example of a net zero carbon school can be found at St Andrews CofE Primary School. | DMAT | Agreed
4.3.2.9
4.3 Schools | Every school should consider: | 9. Promoting walking buses and to use sustainable transport where possible, and to plan for the installation of Electric Vehicle charging points where applicable (as recommended in the DfE draft Sustainability and Climate Change Strategy). Schools could work with local authorities to develop local travel action plans for safe active travel infrastructure around schools. Schools could review their programme of school trips, calculating the carbon emissions from these and reviewing the potential for trips with lower carbon emissions. Travel milestones are presented in Section 5.3. | VA schools | Refer to comments above regarding GEM's property management plan. | 1) encourage schools to work with their families on home-to-school travel |  |  |  |  | can be covered within existing resources |  | 2
4.3 Schools | Every school should consider: | 9. Promoting walking buses and to use sustainable transport where possible, and to plan for the installation of Electric Vehicle charging points where applicable (as recommended in the DfE draft Sustainability and Climate Change Strategy). Schools could work with local authorities to develop local travel action plans for safe active travel infrastructure around schools. Schools could review their programme of school trips, calculating the carbon emissions from these and reviewing the potential for trips with lower carbon emissions. Travel milestones are presented in Section 5.3. | DMAT | Agreed
4.3.2.10
4.3 Schools | Every school should consider: | 10. The habits of each school community and think about offsetting the carbon that schools cannot avoid using. For example, there could be a multi-year plan with ideas on how to reduce energy consumption and travel, fund-raise for charging points, plant trees, or offset in other creative ways. | VA schools | Refer to comments above regarding GEM's property management plan. | 1) develop a network of schools who are working on raising NZC and enbironment generally with their communities. 2) check with national team over promotion of schemes such as https://www.eco-schools.org.uk/ | this is not realaly about money but hearts & minds
4.3 Schools | Every school should consider: | 10. The habits of each school community and think about offsetting the carbon that schools cannot avoid using. For example, there could be a multi-year plan with ideas on how to reduce energy consumption and travel, fund-raise for charging points, plant trees, or offset in other creative ways. | DMAT | Agreed
4.3.2.11
4.3 Schools | Every school should consider: | 11. Integrating the environment into the school programme; from utilising data from smart meters within the classroom to inspire sustainable habits, to exploring the grounds of the adjoining church yard and looking at plants to learn new scientific knowledge and skills. Identify and outline ways to teach this agenda, with a commitment to share resources where possible with their local church, and to share stories and experiences. This also helps to encourage community projects, such as shared electric vehicle charging points. | VA schools | Diocese to determine if such meters are provided and fitted free and if not establish a means to fund such installations. | 1) smart meters are often provided by suppliers (free of charge for householders) - check and promote 2) promote innovative environmental education (I was about to establish a link with an ARU academic who was working on this, but she moved to another university. We can look around for other help |  |  |  |  | can be covered within existing resources | 1
4.3 Schools | Every school should consider: | 11. Integrating the environment into the school programme; from utilising data from smart meters within the classroom to inspire sustainable habits, to exploring the grounds of the adjoining church yard and looking at plants to learn new scientific knowledge and skills. Identify and outline ways to teach this agenda, with a commitment to share resources where possible with their local church, and to share stories and experiences. This also helps to encourage community projects, such as shared electric vehicle charging points. | DMAT | Agreed
4.3.2.12
4.3 Schools | Every school should consider: | 12. Although not within the scope of the net zero carbon 2030 target, schools can consider other environmental policies such as creating recycling points which can be used by the whole community, for example battery recycling. | VA schools | Refer to comments above regarding GEM's property management plan. | this is all part of an educational strategy in schools. They will determine this themselves, but the diocese can play a key role in encouragement and linking
4.3 Schools | Every school should consider: | 12. Although not within the scope of the net zero carbon 2030 target, schools can consider other environmental policies such as creating recycling points which can be used by the whole community, for example battery recycling. | DMAT | Agreed
4.3.2.13
4.3 Schools | Every school should consider: | 13. With National and Diocesan support, encourage schools, children and young people to produce key documents (flyers, presentations, info sheets etc.) to make the declaration to work toward net zero carbon visible to the community. | VA schools | Refer to comments above regarding GEM's property management plan. | this is all part of an educational strategy in schools. They will determine this themselves, but the diocese can play a key role in encouragement and linking
4.3 Schools | Every school should consider: | 13. With National and Diocesan support, encourage schools, children and young people to produce key documents (flyers, presentations, info sheets etc.) to make the declaration to work toward net zero carbon visible to the community. | DMAT | Agreed
4.4.0.2
4.4 Clergy housing | Milestone | 4.4.2. Housing Management: All dioceses and the NCIs to have retrofitting and maintenance plans in place. These should include a Heating Resilience Plan which should consider how to manage heat should the existing system fail to avoid needing a quick like-for-like fossil-fuel replacement. | housing | Highly relevant. High priority. Assessing alternate heating strategy and insulation (interior or exterior cladding may also be considered). Costs: heatpump systems are bespoke, eg, insulation levels, size of property. We have our own design and fit team. Insulation of wall cavities and lofts is not particularly disruptive. Insulation of floors is, very. High-tog carpets and underlay could help. NOTE from conversation: Worcester boilers are hydrogen compatible, but doubts if hydrogen will happen; ASHPs need new pipework and not just new rads; how can one heat a sitting room up in an evening? - need extra source of heat, but woodburners are expensive to install and are air polluting | 1) Develop retrofitting/decarbonisation/stock-improvement plan for each property (with an estimated timetable related to anticipated specific vacancies (eg retirements) and average turnover) // 2) Maintenance plans already in place // 3) develop Heating Resilience Plans for each property |  | 2023 | For 1 and 3: 2025 | Work started | This will require thoughtful reflection on the reports for each property. The first plans will take longer to prepare and then later ones will be faster as can adapt the work on earlier plans. // Details to go into the later Action Plan, but early estimate is 75 hours for housing manager and 75 hours for NZC officer [the NZC officer will need relevant expertise to help with this] |  |  | 25 | No | Housing manager's time will need to be released by the NZC admin; NZC officer's time will be included as a major task of the role. | At the point of upgrading properties, the capital costs will be high. Currently estimates: Average PV install £15k, average ASHP install & design £35k. Insulation costs less. | Some running costs may be higher, at least at first, until fossil fuel prices rise significantly above the cost of electricity times the Coefficient of Performance. Then savings will benefit occupiers. | No savings for DBF, perhaps, but the houses may be worth more money as a result of the works. There will come a time where letting in between incumbencies will be difficult without a high EPC rating | Not possible | Use of NZC grant for the surveys // stock improvement plans will need to be funded largely out of diocesan funds, though look for government grants and incentives etc |  | Fundraising: https://www.altoenergy.co.uk/government/boiler-upgrade-scheme | individual audits of property | not applicable | not applicable |  | Property Manager | Houses Sub-Committee responsible to Finance Committee
4.4.0.3
4.4 Clergy housing | Milestone | 4.4.3. Dioceses: All dioceses to have commissioned stock surveys such as EPC+ reports for at least a representative sample of clergy housing. | housing | Relevant. High priority. Cost. Commissioned for all houses. Question mark whether its worth the paper its written on | Reports for entire housing stock deadline date 31-12-23 |  | 2023 | 2023 | should be done | minimal impact |  |  | 15 | Yes | charges from external consultants | not applicable | not applicable | not applicable | yes | not applicable | not applicable | not applicable | being gathered | not applicable | no | not applicable | Property Manager | Houses Sub-Committee responsible to Finance Committee
4.4.0.4
4.4 Clergy housing | Milestone | 4.4.4. Housing Management: All dioceses, the NCIs and the Pensions Board to have run switching campaigns to encourage occupiers to switch to ‘green’ electricity and, having reviewed options to replace fossil fuels, any building remaining with gas heating should be encouraged to switch to green gas tariffs at the point of contract renewal*, based on national advice about the criteria to apply. | housing | Moderately. Medium. Occupants can pick their preferred energy tariffs. This will be part of general diocesan comms campaign | work with Comms department // NB about 10% of propeties are let and so there will need to be a special comms strategy for non-clergy occupants |  | 2024 | 2024 | at least one communication to occupants | minimal impact | 1 |  | 5 | no | No | not applicable | not applicable | not applicable | yes | not applicable | not applicable | not applicable | being gathered | no | no | dependant entirely on response from occupiers. No. No | Comms team primarily | Houses Sub-Committee responsible to Finance Committee
4.4.0.5
4.4 Clergy housing | Milestone | 4.4.5. Dioceses: All dioceses to have stock improvement plans in place, having regard to the timing of when properties become vacant. The plan should make reference to the Practical Path to Net Zero for Clergy Housing (Milestone 4.4.1) and actively consider implementation of ‘quick wins’, how to decarbonise heat and how to reduce energy consumption. | housing | Very relevant. High. We can undertake work to bring a house up to Minimum Standards, but many 'quick wins' are; a) Dependent on actions of occupiers. We can encourage occupiers to adopt measures, but not require them to, b) not dependent on waiting until houses are vacant. N.B. The PPNZ for clergy houses is not yet published. | The retrofitting/decarb plans will largely depend on vacancies. Some vancancies can be anticipated and planned for, many can't. This work needs to be opportunistic, but budgeting will be helped by some sort of prediction over how many might be tackled in any specific year. We review and undertake 'dirty work' when properties are vacant. // the heating resilience plans will be acted upon when heating systems suddenly fail // Housing Committee will need to agree a performance specification for its properties, setting a minimum standard |  | 2024 | develop retrofit and resilience plans in 2025 | General plans already in place, but the NZC developments will not be ready until 2025 | see milestone 4.4.2 |  |  | 20 | [13 empty] | Property Manager | Houses Sub-Committee responsible to Finance Committee
4.4.0.8
4.4 Clergy housing | Milestone | 4.4.8. Housing Management: At change of occupancy, and no later than 2030, install smart meters to assist with monitoring and management of energy consumption. | housing | Reliant on occupants. Low. Can only be instructed directly by occupants | as part of comms plan, encourage occupants to ask for smart meters. LED light bulbs are already being replaced at each vacancy |  | 2030 | 2024 to send first communication and commence vacancy fittings | perhaps 10 properties changed at a vacancy; 20 changed by occupants - but that depends on them | minimal |  |  |  | no | not applicable | not applicable | not applicable | not applicable | not applicable | none | not applicable | not applicable | not applicable | not applicable | not applicable | not relevant | Property Manager | Houses Sub-Committee responsible to Finance Committee
4.4.1.1
4.4 Clergy housing | housing managers should consider: | 1. Developing maintenance plans: All dioceses should have good records of the condition of their housing stock from the Quinquennial Inspections required every five years. These reports should identify works that can be carried out immediately, or within the next five years, that will help identify what maintenance works will help reduce energy waste; for example, replacing worn window seals and regular servicing of boilers and other heat sources. Dioceses should use this information to develop maintenance plans, leading to a programme of works. The Pensions Board should take a similar approach. | housing | Yes and we do | The NZC element is discussed under the milestones above
4.4.1.2
4.4 Clergy housing | housing managers should consider: | 2. Understanding stock condition: The Energy Footprint Tool allows dioceses to calculate the carbon footprint from clergy housing using an EPC. Some dioceses and parishes have started commissioning reports on their housing portfolios to help them plan for change, and a few have already started a programme of works focussing first on ‘easy wins’. Dioceses are increasingly talking to each other to learn from the experience of those who are further ahead. There is now a recognition that a better quality of survey of our housing is needed, than the standard ‘house purchaser type EPC’. The quality of these EPC reports can vary significantly and the recommended works arising from those reports are too limited in scope. EPC Plus reports cover a broader scope. | housing | Relevant. We are monitoring national debate on the accuracy of EPC and EPC Plus reports in connection with carbon reduction and energy saving. Anecdotal evidence many house purchaser EPCs are broadly rubbish. We are relient on a national improvement of these reporting standards to progress sensibly using these measurements | We are commissioning audits as explained above
4.4.1.3
4.4 Clergy housing | housing managers should consider: | 3. Developing stock improvement plans: From the EPC Plus reports, a programme of works can be produced. The quality of our housing stock needs to improve significantly, meaning significant capital investment. The improvements should be focussed on the source of heating (replacing fossil fuel boilers) and heat retention capability. It remains to be seen whether the existing gas network can be re-used with hydrogen. Therefore, renewable energy solutions such as ground/air-source heat pumps, and (for off-grid applications), biomass boilers are likely to be seen as priority projects given the timescales we are working to. For buildings older than ten years, heat pump installation should be accompanied by insulation of walls, floors and roofs to improve energy efficiency. All of this work is highly disruptive and not to be recommended while a property is occupied. It needs to be recognised that most housing cannot be made entirely carbon neutral, but meaningful energy efficiencies can be achieved through good insulation and glazing improvements. Any building undergoing a major renovation should be prioritised for heat pump retrofit. Stock improvement plans should also assess the options for a building – whether to keep, retrofit or replace. | housing | Very. Medium to high. Costs. The base line of our housing stock will be higher than that of many other dioceses. We are reactive to Building Regulations which are already requiring changes and will change more significantly in 2025 | see milestones above
4.4.1.4
4.4 Clergy housing | housing managers should consider: | 4. QI Inspections: Consider reviewing QI inspection template to identify the current EPC rating where available and the opportunities for energy efficiency measures. | housing | Yes. medium. None in terms of identification, after that upgrade may have cost implications | Work with other E of England dioceses on a QI template |  |  | 2024 |  | minimal in that these are already done by the Property Manager (takes about 1hr per property)
4.4.1.5
4.4 Clergy housing | housing managers should consider: | 5. EV charging: Review the potential for installation of electric vehicle (EV) charging points (where off-street parking is available) at change of occupancy. See also Section 5.3. | housing | The Houses Committee is developing a policy for EV charges. At point of survey the installation of EV charge points will be considered but not guaranteed. | This will be part of the audit process, but will also be responsive to requests from occupiers
4.4.1.6
4.4 Clergy housing | housing managers should consider: | 6. Solar PV: Review the potential for installation of solar photo-voltaic panels (with battery if appropriate) at change of occupancy, or as part of a review of renewable potential across the estate. | housing | Yes. medium. A whole estate review, after that upgrade will have significant cost implications. | The NZC team will be looking at the potential for a company to review PV across the diocese. We might test the water with clergy housing before turning to churches
4.4.1.7
4.4 Clergy housing | housing managers should consider: | 7. Electric cookers: Encourage tenants to replace existing gas cookers with energy-efficient electric cookers at end-of-life. | housing | We don’t provide cookers. Yes. medium. None in terms of identification | Housing Committee to discuss whether to remove fittings for gas cookers at vacancies |  |  | 2026
4.4.1.8
4.4 Clergy housing | housing managers should consider: | 8. Reviewing government incentives: The UK government announced VAT relief on energy saving materials for residential accommodation in the Spring Statement 20226 7 and the Boiler Upgrade Scheme from April 2022. | housing | NOTE from GH: VAT relief can only have a 20% impact, but the grants towards heatpumps are £5,000 - I think enough to make it less than the cost of a new gas boiler, provided existing distribution system can be used ??? PM says its likely to be the same | NZC team to keep eye on incentive schemes
4.6.0.1
4.6 Offices | Milestone | 4.6.1. Office Management: All offices to register for Eco Church during 2022 and aim to achieve a bronze Eco Church award by 2023 and silver by 2026. | central | This will need to wait until the new building is up | register and apply for Bronze |  | 2022-2026 | 2025 | [18 empty] | Adam Evans
4.6.0.2
4.6 Offices | Milestone | 4.6.2. Office Management: All offices to measure and report on their carbon emissions by inputting utility bill information and floor area into the Energy Footprint Tool. | central | This will need to wait until the new building is up | input energy data |  | 2023+ | 2025 | [18 empty] | Adam Evans
4.6.0.3
4.6 Offices | Milestone | 4.6.3. Office Management: All offices have at least a high-level Net Zero Carbon Action Plan, including some consideration of space availability and needs. The plan should actively consider implementation of ‘quick wins’, how to decarbonise heat and how to reduce energy consumption. The Action Plan should also contain a Heating Resilience Plan which should consider how to manage heat should the existing system fail to avoid needing a quick like-for-like fossil-fuel replacement. | central | All these points have been incorporated into the plans for the new office building | the plan has been achieved |  | 2023 | 2023 | [18 empty] | Adam Evans
4.6.0.4
4.6 Offices | Milestone | 4.6.4. Office Management: Offices to review the potential for installation of electric vehicle charging points and the provision of dedicated car parking spaces for electric cars. If appropriate, then move ahead to installation. | central |  | 4 will be provided in the new build, with the potential for a further 8 as need develops |  | 2023-24 | 2025 | [18 empty] | Adam Evans
4.6.0.5
4.6 Offices | Milestone | 4.6.5. Office Management: From 2023 onwards, all offices not already on one to switch to a green electricity tariff at the point of contract renewal.* | central | potential but pv on roof, no battery | 1) roof PV will mean that very little electricity will be drawn from the grid 2) look to a contract that makes most sense for the contribution PV can make to the grid, which may mean it is not a fully green tariff |  | 2024 | [19 empty] | Adam Evans
4.6.0.6
4.6 Offices | Milestone | 4.6.6. Office Management: From 2024 onwards*, and having reviewed options to replace fossil fuels, all offices that remain on gas heating switch to a ‘green’ gas tariff at the point of contract renewal, based on national advice about the criteria to apply. | central | none; offset export PV |  |  | 2024
4.6.0.7
4.6 Offices | Milestone | 4.6.7. Office Management: No new or replacement oil boilers to be installed in offices after this date.* | central |  |  |  | 2025
4.6.0.8
4.6 Offices | Milestone | 4.6.8. Office Management: All owned offices to deliver the actions in their Net Zero Carbon Action Plans. | central |  |  |  | 2030 | [19 empty] | Adam Evans
4.6.1.1
4.6 Offices | office managers should consider: | 1. Reviewing how offices are used, in terms of physical meetings, desk utilisation, and room rental. Simple layout changes can improve energy efficiency9. Decide if you are in the right building. | central | done
4.6 Offices | office managers should consider: | 2. Adopting a policy of ‘flexible working’ to allow staff, where it is appropriate, to work from home. Each situation is different, but it may reduce energy consumption within the building and reduce carbon emissions from travel to work (not currently included in scope). Once adopted, review desk utilisation as it may be possible to reduce the size of office buildings, thereby reducing energy costs and carbon emissions. | central | done
4.6 Offices | office managers should consider: | 3. Taking advice from an energy consultant. | central
4.6 Offices | office managers should consider: | 4. Engaging with your staff, in order to work towards behavioural change. Carbon Literacy training can be a good option here, and national ‘train the trainer’ sessions have already been run in 2022, and more are planned. | central |  | part of training for new building after 4 years wfh. Note to include this
4.6 Offices | office managers should consider: | 5. Using your Net Zero Carbon Action Plan, action the quick wins for reducing energy consumption – not leaving equipment on standby, turning off lights when leaving rooms, replacing lights with LEDs, appropriate heating and air-con settings etc. | central | part traing and PIR activated, bldg manage syst
4.6 Offices | office managers should consider: | 6. Budgeting and work towards major project work. | central | dir planning | [22 empty] | forthcoming Director of Planning
4.6 Offices | office managers should consider: | 7. Reviewing the potential for sustainable travel to the office: secure parking for bicycles, scooters and motorcyclists, changing and storage facilities for cyclists, and to install electric bike and vehicle charging points. Consider developing a Travel Plan for the office that incorporates the Travel Hierarchy, and offers staff benefits such as the Government’s Cycle to Work Scheme. See also Section 5.3 for further ideas. | central | Provision for the physical elements is made in the new office development | include in the forthcoming Travel Plan | [21 empty] | Sheena Bridgeman
4.6 Offices | office managers should consider: | 8. Ensuring equipment replacements are energy efficient. | central |  | part of new office development | [21 empty] | Adam Evans
5.1.0.3
5.1 Communications, etc and leadership | Milestone | 5.1.3. Dioceses: Dioceses to create a Routemap to Net Zero Carbon by 2030 Communications Strategy. Net Zero Carbon messages to be incorporated in ongoing communications by Diocesan Communications Officers, Schools communications teams and Church communications, throughout the decade, with interest groups (e.g. DEOs) providing feedback. | M&M & Comms | Linked with 4.1. Work with the Diocesan Environmental Lead to produce a route to net zero plan that could be followed by the majority of churches and schools. The communications element then builds on top of this core plan. The Strategic plan is developed first, the comms approach and timelines then sit on top of this to compliment and promote the activities of the other departments and to broadcast the tools available to all to help realise their own targets. | Work with the environmental lead to agree the overall structuire of approach (i.e. to be bult around the 5 marks of mission), incorporate activity workstreams into the strategy leveraging the key deliverables expected from the staff directly employed centrally to support the promotion of net zero. Measure success by succesful award of Eco Church status. | 1) largely see line 5 2) discuss with senior clergy how they can include NZC messaging in their communications to give it a salient profile in the diocese - they may be helped if this is part of a diocesan-wide key theme of communication | 2022+ | 2) 2024 Q1 |  | up front 20 hours to produce the plan, then 2-3 hours per week (across all comms activities) to deliver the messaging. | 10 | 10 | 10 | Will there be examples of other national diocesan examples of communication best practivce one might be able to acces and utlise? | three core staff delivering engagement of NCZ plan will incur costs | [7 empty] | feedback from schools and parishes via the Environmental team |  |  |  | Head of Cimmunications and Deputy Director of M&M & Bps advisers
5.1 Communications, etc and leadership | Milestone | 5.1.3. Dioceses: Dioceses to create a Routemap to Net Zero Carbon by 2030 Communications Strategy. Net Zero Carbon messages to be incorporated in ongoing communications by Diocesan Communications Officers, Schools communications teams and Church communications, throughout the decade, with interest groups (e.g. DEOs) providing feedback. | parish buildings | Comms strategy starts with the internal departmental comms (this document), and will roll out from there. James O to remain with overall oversight? | I suppose so | we should encouragae a good comms strategy | 2022+
5.1 Communications, etc and leadership | Milestone | 5.1.3. Dioceses: Dioceses to create a Routemap to Net Zero Carbon by 2030 Communications Strategy. Net Zero Carbon messages to be incorporated in ongoing communications by Diocesan Communications Officers, Schools communications teams and Church communications, throughout the decade, with interest groups (e.g. DEOs) providing feedback. | parishes gen |  |  | this overlaps considerably with much of the work in this tab | 2022+
5.1 Communications, etc and leadership | Milestone | 5.1.3. Dioceses: Dioceses to create a Routemap to Net Zero Carbon by 2030 Communications Strategy. Net Zero Carbon messages to be incorporated in ongoing communications by Diocesan Communications Officers, Schools communications teams and Church communications, throughout the decade, with interest groups (e.g. DEOs) providing feedback. | VA schools |  | 1) identify staff member to collaborate on diocesan comms strategy | we need the education team to be part of the diocesan comms strategy | 2022+ |  |  | can be covered within existing resources | [16 empty] | Jacqueline McCamphill
5.1.1.1
5.1 Communications, etc and leadership | Dioceses should consider: | 1. Developing a clear and engaging communications campaign, covering all stakeholder groups, and ensure key messages are shared widely and consistently. Build on and localise the national communications strategy and make use of national materials where locally useful. | M&M & Comms | The local comms plan should be appropriate to the targets of the local NCZ Plan and be appropriate to what is reasonable for the parishes to realise. |  | this is just good general advice | [20 empty] | Head of Cimmunications and Deputy Director of M&M & Bps advisers
5.1.1.2
5.1 Communications, etc and leadership | Dioceses should consider: | 2. Communicating progress on Eco Diocese and share ways in which progress has been made with others. Also promote Eco Church - see Milestones 4.2.9, 4.5.5 and 4.6.1 | M&M & Comms | Essential as a primary measure of being able to track general progress. Eco Church award will by default indicate progression towards a improved postion. |  | include EcoChurch and EcoDiocese messages in communications | [20 empty] | Head of Cimmunications and Deputy Director of M&M
5.1.1.3
5.1 Communications, etc and leadership | Dioceses should consider: | 3. Collaborating across dioceses in regional groups (such as those which Diocesan Secretaries belong to) to trouble-shoot, share best practice, make easier access to case studies and maintain momentum by providing peer support. | M&M & Comms | The national comms network exists in order to help facilitate the sharing of information. |  | 1) Engage with the Eastern Region dioceses NZC hub and through that with the Comms and M&M teams in the other dioceses and 2) ask the NZC regional hub person to engage with the M&M people |  |  |  |  | 2 | 2 | 4 | [13 empty] | Head of Cimmunications and Deputy Director of M&M
5.1.1.4
5.1 Communications, etc and leadership | Dioceses should consider: | 4. Integrating questions into Archdeacon’s articles of enquiry. Archdeacons are key because they contact all churches at times of change. | M&M & Comms | Artcles have not been done since prior to covid, when/if they return, the (Church buildings?) team may have a role in posing questions around net carbon. Communications to be mindful of this and to also consider shaping questions to ask whether enough is also be communcated in the broadest sense from the central comms team.
5.1 Communications, etc and leadership | Dioceses should consider: | 4. Integrating questions into Archdeacon’s articles of enquiry. Archdeacons are key because they contact all churches at times of change. | parishes gen | For archdeacons |  | Ads to encourage benefices to include something in Parish Profiles when seeking new incumbents [implies also at time of writing parish profiles] | [5 empty] | 2 | 4
5.1.1.5
5.1 Communications, etc and leadership | Dioceses should consider: | 5. Dioceses can use advocacy for environmental change. | M&M & Comms |  |  | 1) include this in the general messaging with links to advocacy groups, both church and secular 2) develop tools and programmes that parishe and schools can pick up and use locally to engage their communities in climate conversations etc; also encouraging parishes to work both ecumenically and with other concerned groups in their communities, including parish councils 3) NZC team to link up with local authorities to collaborate on messaging in appropriate circumstances | [5 empty] | 3
5.1.2.1
5.1 Communications, etc and leadership | Parishes should consider: | 1. Joining the Eco Church scheme, which is identified as a significant vehicle for driving engagement and commitment at parish level and ties in with the Eco Diocese scheme above. | parishes gen | Ensure that our messaging is focussed on encouraging parishes to join the Eco Church, and make use of their audit tools.
5.1.2.2
5.1 Communications, etc and leadership | Parishes should consider: | 2. Committing to sharing experiences (good and bad) via the DEO, Area Deans or Archdeacons. | parishes gen | Eco-Network lunches already happening | Monthly Eco-Mailing. Evaluate success of network lunches. Launch Eco-form (zoom).
5.1.3.1
5.1 Communications, etc and leadership | Schools should consider: | 1. Using the Let’s Go Zero campaign as one way to encourage schools and students to take action | VA schools | Refer to comment above about the need for the Diocese to identify and develop a partnership with relevant organisations and promote finding and updates to schools. | like EcoSchools but https://letsgozero.org/
5.1.3.2
5.1 Communications, etc and leadership | Schools should consider: | 2. See also school action points in Section 4.3 Schools. | VA schools |  | already covered
5.1.4.1
5.1 Communications, etc and leadership | Individuals should consider: | 1. Christians can get involved locally in public debate to influence policies that make decarbonisation easier to achieve. | parishes gen |  | This is a critical time of manifestowriting by parties. Parishes could both lobby themselves, encourage members to lobby, and, especially, engage with their communities to raise env profile // there is some national work starting on this. I have a draft of a programme for a listening exercise meeting | 1) highlight the community engagement element of the EcoChurch programme 2) develop a simple model event for parishes to roll out to help local people to listen ton one another about climate 3) encourage enagement with local authorities - parishes with their local Members, DEO with County and Combined Authority |  |  |  | DEO 4d |  | 3
5.2.0.10
5.2 Capacity-building | Milestone | 5.2.10. Dioceses: Individually, or in regional groups, all dioceses to review their capacity to respond to the Routemap and identify gaps. The review should cover (i) the capacity to engage schools, archdeacons, deaneries, and churches across the diocese, (ii) the project management skills needed to initiate and support local action, (iii) the technical input needed and (iv) the local fundraising capacity needed. | M&M & Comms | The Communications Team has a role to play to liaise with other external Diocese colleagues to understand the national and regional plans that are being developed and to help ensure best practice is seen and shared where sensible to do so. | The Comms teams natioanlly meet regulalrly (via Zoom) and the environment is a frequent feature in this). | I sense that you do not see that there are any capacity gaps in Comms that could be usefully addressed. Is that right? | 2023 | 2023+ | [18 empty] | Environmental Officer
5.2 Capacity-building | Milestone | 5.2.10. Dioceses: Individually, or in regional groups, all dioceses to review their capacity to respond to the Routemap and identify gaps. The review should cover (i) the capacity to engage schools, archdeacons, deaneries, and churches across the diocese, (ii) the project management skills needed to initiate and support local action, (iii) the technical input needed and (iv) the local fundraising capacity needed. | parish buildings | Much of this will be covered in the revitalised DETG. | there is also the challenge/opportunity of plugging gaps through the regional collaboration | The revitalised DETG and the NZC subgroup // use the regional collaboration to advise 'at the end of a phone' rather than make site visits; sharing publications and presentations - also national Moodle // capacity to engage is not so much a skills-gap as a resource gapm as far as churches are concerned (eg comments about visits just above); I am not sure visiting Deanery chapters or synods is worth while, I think visits have to be at benefice or parish level and engage both clergy and leading layity // project management - the idea is that HoDs already have this to a degree and will now apply it to NZC work as to their established work; for parishes, they will need to turn to their specialist advisers (at a cost), eg look how King's got OC to do all their project management; do we need a Hollie type person - I am not really clear on what input she does give parishes // technical - may partly be covered by new NZC grant-funded staff, but also through DAC recruitment (can this expertise be shared with housing and schools?) // fundraising - refer to M&M | 2023 |  |  |  | 2 | 2
5.2 Capacity-building | Milestone | 5.2.10. Dioceses: Individually, or in regional groups, all dioceses to review their capacity to respond to the Routemap and identify gaps. The review should cover (i) the capacity to engage schools, archdeacons, deaneries, and churches across the diocese, (ii) the project management skills needed to initiate and support local action, (iii) the technical input needed and (iv) the local fundraising capacity needed. | strategy |  | this is partly done under each tab // the regional group should work at this too |  | 2023 | 2024 |  | DEO 6d ; NZC 6d | 6 | 6
5.2 Capacity-building | Milestone | 5.2.10. Dioceses: Individually, or in regional groups, all dioceses to review their capacity to respond to the Routemap and identify gaps. The review should cover (i) the capacity to engage schools, archdeacons, deaneries, and churches across the diocese, (ii) the project management skills needed to initiate and support local action, (iii) the technical input needed and (iv) the local fundraising capacity needed. | housing | Collaboration across the E of England diocesan housing managers is already happening | develop this |  | 2023 | 2024 |  | For regional meetings [2hr every 2 months] and other collaboration: DEO 8d; NZC 8d, but this should be offset by shared work - and see above | 8 | 8
5.2 Capacity-building | Milestone | 5.2.10. Dioceses: Individually, or in regional groups, all dioceses to review their capacity to respond to the Routemap and identify gaps. The review should cover (i) the capacity to engage schools, archdeacons, deaneries, and churches across the diocese, (ii) the project management skills needed to initiate and support local action, (iii) the technical input needed and (iv) the local fundraising capacity needed. | VA schools | Noted | Has the education team reflected on its capacity to support schools in this work? With the new Eastern Region Diocesan hub, it should be easier to draw on the expertise of other DEBs locally |  | 2023 | [19 empty] | Jacqueline McCamphill | Diocesan Board of Education
5.2 Capacity-building | Milestone | 5.2.10. Dioceses: Individually, or in regional groups, all dioceses to review their capacity to respond to the Routemap and identify gaps. The review should cover (i) the capacity to engage schools, archdeacons, deaneries, and churches across the diocese, (ii) the project management skills needed to initiate and support local action, (iii) the technical input needed and (iv) the local fundraising capacity needed. | DMAT | Technical skills from independent specialists is a key factor in producing the right solution / part solution for schools. There is no point specifying kit that will not effectively heat / provide hot water, or cost the school so much in utility bills that it is detrimental to run. Not every 'specialist' truly knows this area of M and E, or assesses the existing buildings correctly. |  |  | 2023
5.2.1.1
5.2 Capacity-building | Dioceses should consider: | 1. Most dioceses have a heating advisor and/or sustainability advisor, but not all; and similarly not all have a Diocesan Environment Officer. These staff/volunteers vary considerably in the time they have and the skills/background they came to the role from. Every diocese is encouraged to invest in these key roles and to include them in decision-making functions. | strategy |  | see buildings tab
5.2 Capacity-building | Dioceses should consider: | 1. Most dioceses have a heating advisor and/or sustainability advisor, but not all; and similarly not all have a Diocesan Environment Officer. These staff/volunteers vary considerably in the time they have and the skills/background they came to the role from. Every diocese is encouraged to invest in these key roles and to include them in decision-making functions. | parish buildings | Wehave all of these, but should expand further as noted above, |  | Wehave all of these, but should expand further as noted above,
5.2.1.2
5.2 Capacity-building | Dioceses should consider: | 2. Discussing with the DAC and Archdeacons how decision-making can best incorporate net zero carbon ambitions. | parish buildings | Enforcing statements of needs better? | not just enforcement - though super important - but we should review the model SoN and provide guidance - except, we hope to borrow another diocese's work as surely others will have done this | see NZC vetting group suggestion; new guidance on use of SoN and on national guidance to turn to // engage chancellor, ? Practice directions // archdeacons involved in 'parishes general' tab |  |  |  |  | 2 | 2
5.2 Capacity-building | Dioceses should consider: | 2. Discussing with the DAC and Archdeacons how decision-making can best incorporate net zero carbon ambitions. | parish buildings | Enforcing statements of needs better? | not just enforcement - though super important - but we should review the model SoN and provide guidance - except, we hope to borrow another diocese's work as surely others will have done this | see NZC vetting group suggestion; new guidance on use of SoN and on national guidance to turn to // engage chancellor, ? Practice directions // archdeacons involved in 'parishes general' tab
5.2 Capacity-building | Dioceses should consider: | 2. Discussing with the DAC and Archdeacons how decision-making can best incorporate net zero carbon ambitions. | parishes gen
5.2.1.3
5.2 Capacity-building | Dioceses should consider: | 3. Making carbon-footprint reporting, and completion of the Energy Footprint Tool, a required element of the APCM each year. | parishes gen | This should just be part of the requirement alongside the parish return. Should it simply be folded into this? |  | APCM is a bit separate
5.2.1.4
5.2 Capacity-building | Dioceses should consider: | 4. Providing a Lay Training Pathway for Parish Environment Officers, as piloted in the Diocese of Leeds. | M&M & Comms |  |  | 1) investigate Leeds programme to see if appropriate for Ely 2) will investigate a possible ALM pathway for ministry on the environment/sustainability (this would be a development into more missional ministries for ALM (speak to Julie Norris and Mark Rodell - Open Christian Learning) 3) (to meet EcoDiocese:) review CMD amd IME2 to see whether the environment element of these can be strengthened - speak to ERMC 4) consider commissioning a TEI to write a course [perhaps £10k to TEI plus in-house time] | [5 empty] | 5 | 5 |  | in house staff time | £10k to TEI
5.2 Capacity-building | Dioceses should consider: | 4. Providing a Lay Training Pathway for Parish Environment Officers, as piloted in the Diocese of Leeds. | parishes gen | For the Lay Training team to establish inter-departmental conversation aroudn the development of targetted training that equips prish environmental lead practitioners. | Ensure that this is an integral part of Open Christian Learning
5.2.1.5
5.2 Capacity-building | Dioceses should consider: | 5. Gathering and sharing case studies. Update church records on the OFS Renewables Map. | strategy |  | see buildings tab | [7 empty] | 10
5.2.1.6
5.2 Capacity-building | Dioceses should consider: | 6. Having a named project manager for delivering net zero carbon. This could be a new role or part of an existing role but would have dedicated time to deliver this work. | parish buildings | We have this (and are seeking funding to extgend it). |  | We have this (and are seeking funding to extgend it).
5.2 Capacity-building | Dioceses should consider: | 6. Having a named project manager for delivering net zero carbon. This could be a new role or part of an existing role but would have dedicated time to deliver this work. | housing |  | The Property Manager | [21 empty] | Property Manager | Houses Sub-Committee responsible to Finance Committee
5.2 Capacity-building | Dioceses should consider: | 6. Having a named project manager for delivering net zero carbon. This could be a new role or part of an existing role but would have dedicated time to deliver this work. | VA schools | Diocese to consider, if not already actioned. | I think this may be you, Jacqueline, for schools | I am taking the lead across the diocese as a whole, though |  |  |  | can be covered within existing resources | [16 empty] | Jacqueline McCamphill
5.2 Capacity-building | Dioceses should consider: | 6. Having a named project manager for delivering net zero carbon. This could be a new role or part of an existing role but would have dedicated time to deliver this work. | DMAT | Again, this person should not be guided by a supplier of products who is very helpful in giving surveys / advice etc.
5.3.0.3
5.3 Work-related travel | Milestone | 5.3.3. Institutions: All dioceses, and where applicable TEIs, schools, offices and the NCIs, to develop or update a Travel Plan that includes ‘no travel’ options. | central |  | Will use one of the two HR consultants used by the diocese. They may have an off-the-shelf Travel Plan that we can adapt |  | 2023+ | 2024 | [18 empty] | Sheena Bridgeman
5.3 Work-related travel | Milestone | 5.3.3. Institutions: All dioceses, and where applicable TEIs, schools, offices and the NCIs, to develop or update a Travel Plan that includes ‘no travel’ options. | VA schools |  | 1) encourage schools to work with their families on home-to-school travel 2) and to develop a travel strategy for staff and school trips |  | 2023+ |  |  | can be covered within existing resources | [16 empty] | Jacqueline McCamphill
5.3.0.4
5.3 Work-related travel | Milestone | 5.3.4. Institutions: All dioceses, and where applicable TEIs, schools, offices and the NCIs, to review and update travel and expenses policies to encourage sustainable transport. | central | will need to be agreed w Fin cttee | This will be included in the Travel Plan |  | 2024+ | 2024 | [18 empty] | Sheena Bridgeman | Finance Committee
5.3 Work-related travel | Milestone | 5.3.4. Institutions: All dioceses, and where applicable TEIs, schools, offices and the NCIs, to review and update travel and expenses policies to encourage sustainable transport. | VA schools |  | as part of 2) above |  | 2024+ | [19 empty] | Jacqueline McCamphill
|  | 5.3.0.6 |  | not applicable
5.3.1.1
5.3 Work-related travel | Every diocesan-level organisation should consider | 1. Promoting the Energy Saving Trust Sustainable Travel Hierarchy10 and encourage it’s use for making travel decisions while considering the greenest mile is the mile not travelled. | central |  | look to include when discussing the Travel Plan
5.3 Work-related travel | Every diocesan-level organisation should consider | 1. Promoting the Energy Saving Trust Sustainable Travel Hierarchy10 and encourage it’s use for making travel decisions while considering the greenest mile is the mile not travelled. | VA schools | Noted to be considered as part of a wider strategy. | as part of 2) above
5.3.1.2
5.3 Work-related travel | Every diocesan-level organisation should consider | 2. Updating expenses policies to encourage sustainable transport, to include consideration to offering UK government mileage rates for cycling, motorbikes and carrying passengers on business. Review opportunities to offer the Government Cycle to Work Scheme to employees. | central |  | look to include when discussing the Travel Plan
5.3.1.3
5.3 Work-related travel | Every diocesan-level organisation should consider | 3. Making all new car purchases non-fossil-fuel vehicles. | central |  | probably not applicable
5.3 Work-related travel | Milestone | 5.3.3. Institutions: All dioceses, and where applicable TEIs, schools, offices and the NCIs, to develop or update a Travel Plan that includes ‘no travel’ options. | parishes gen |  | Also at diocesan level: be intentional in planning travel, encourage car sharing (share emails with permission), consider how many delegates to send to meetings, consider if can be done by Zoom/Teams // generally "think about it before you get into your car" | we should encourage parishes to review their travel expenses policy and also other travel issues | 2023+ |  |  |  | 3 | 1
5.3.1.4
5.3 Work-related travel | Milestone | 5.3.4. Institutions: All dioceses, and where applicable TEIs, schools, offices and the NCIs, to review and update travel and expenses policies to encourage sustainable transport. | parishes gen |  |  | ditto | 2024+
5.3.1.7
5.3 Work-related travel | Every diocesan-level organisation should consider | 7. Reviewing opportunities and options to install charging for electric vehicles and bikes, secure storage for bikes, scooters and motorbikes and changing facilities/lockers at all building types, where appropriate to encourage behaviour change. Installation of EV charging may be eligible for funding through the UK government EV ChargePoint grant scheme or the workplace charging scheme11. | parishes gen |  |  | I think this would only apply to a few churches
5.3 Work-related travel | Every diocesan-level organisation should consider | 7. Reviewing opportunities and options to install charging for electric vehicles and bikes, secure storage for bikes, scooters and motorbikes and changing facilities/lockers at all building types, where appropriate to encourage behaviour change. Installation of EV charging may be eligible for funding through the UK government EV ChargePoint grant scheme or the workplace charging scheme11. | VA schools | Noted to be considered as part of a wider strategy. |  | this will be a funding issue, but it may be relatively cheap and a possible project for PTAs
5.3.1.9
5.3 Work-related travel | Every diocesan-level organisation should consider | 9. Developing and sharing a recommended school coach hire policy which suggests the use of low-carbon transport wherever possible and contains a sustainable coach hire hierarchy (e.g. public transport has been assessed as not feasible therefore: hire an electric coach, hire a biofuel coach, hire an ultra-low emission coach, use a coach of the correct size). | VA schools | Refer to comments above regarding GEM's property management plan. | 1) ask schools if they have any recommendations they could pass on to others
5.3 Work-related travel | Every diocesan-level organisation should consider | 9. Developing and sharing a recommended school coach hire policy which suggests the use of low-carbon transport wherever possible and contains a sustainable coach hire hierarchy (e.g. public transport has been assessed as not feasible therefore: hire an electric coach, hire a biofuel coach, hire an ultra-low emission coach, use a coach of the correct size). | DMAT | Agreed
5.4.1.1
5.4 Funding options | Dioceses and others should consider: | 1. Preparing for funding opportunities, through carrying out energy audits, heat decarbonisation plans, and/or Net Zero Carbon Action Plans. Commission reviews of opportunities for renewables on Church-owned buildings and land. Know what works needs to be done, what it costs, and be clear on the benefits and the case for funding. Work with finance teams to create cases for lending/investment. | parish buildings | "Preparing for funding opportnities" - an enigmatic suggestion. I assume this means if we can show a certain project in a certain church will have a net zero outcome, that project is more likely to get NZC funding from the next tranche? | Well, it might, but I think they are also thinking of other funding opps coming along (they live a life of prayer). This would be relevant to schools, but surely not to churches, unless a new Labour government miraculously manages to square the accounts and give money to decarbonising. (eat drink and be merrty for tomorrow we die) | This is not very feasible for churches as unlikely there will be many opportunities (unlike for schools and residential houses that may be funded by future governments); there may be v limited funding for some trial cases in the next triennium |  |  |  |  | 7
5.4 Funding options | Dioceses and others should consider: | 1. Preparing for funding opportunities, through carrying out energy audits, heat decarbonisation plans, and/or Net Zero Carbon Action Plans. Commission reviews of opportunities for renewables on Church-owned buildings and land. Know what works needs to be done, what it costs, and be clear on the benefits and the case for funding. Work with finance teams to create cases for lending/investment. | housing |  | this will flow from the audits | [5 empty] | 4
5.4 Funding options | Dioceses and others should consider: | 1. Preparing for funding opportunities, through carrying out energy audits, heat decarbonisation plans, and/or Net Zero Carbon Action Plans. Commission reviews of opportunities for renewables on Church-owned buildings and land. Know what works needs to be done, what it costs, and be clear on the benefits and the case for funding. Work with finance teams to create cases for lending/investment. | VA schools | Refer to comments above. Diocese to develop partnership arrangements whereby they are informed of funding opportunities. |  | the church buildings team are thinking about this |  |  |  |  | 2
6.1.0.4
6.1 Offsetting | Milestone | 6.1.4. Dioceses and Institutions: Implement carbon offsetting with an approved supplier to offset those emissions that have been impossible to eliminate. | strategy |  | 1) DEO to investigate in due course |  | 2030+ | 2028 |  | 5d |  | 5
6.1 Offsetting | In Ely diocese | 1. Whether families that are within influence of a church or school might invest in their own home buildings, when they would not otherwise have done, and the energy saved recorded as a contribution towards the net carbon status of the church/school. | parishes gen |  |  | is this a good idea? | [5 empty] | 3
6.1 Offsetting | In Ely diocese | 1. Whether families that are within influence of a church or school might invest in their own home buildings, when they would not otherwise have done, and the energy saved recorded as a contribution towards the net carbon status of the church/school. | VA schools | Noted to be considered as part of a wider strategy. | 1) education team to reflect on whether this is a good idea | This can be an individcual school strategy
6.1 Offsetting | In Ely diocese | 1. Whether families that are within influence of a church or school might invest in their own home buildings, when they would not otherwise have done, and the energy saved recorded as a contribution towards the net carbon status of the church/school. | DMAT | Agreed
6.1 Offsetting | In Ely diocese | 2. Whether families that are within the influence of a church or school might collaborate in campaigning to persuade elected leaders (local or national) to make changes that would make carbon saving easier and cheaper for ordinary buildings and travel. | parishes gen |  |  | see line above about manifestos
6.1 Offsetting | In Ely diocese | 2. Whether families that are within the influence of a church or school might collaborate in campaigning to persuade elected leaders (local or national) to make changes that would make carbon saving easier and cheaper for ordinary buildings and travel. | VA schools | Noted to be considered as part of a wider strategy. | 1 this is part of the education/community work discussed above
6.1 Offsetting | In Ely diocese | 2. Whether families that are within the influence of a church or school might collaborate in campaigning to persuade elected leaders (local or national) to make changes that would make carbon saving easier and cheaper for ordinary buildings and travel. | DMAT | Agreed
6.2.0.2
6.2 Church land | Milestone | 6.2.2. Dioceses to review with their land agents the terms of tenancy agreements to include net zero and biodiversity ambitions. | glebe | Important see below. If we are all striving for the same target. Can we piggy back off the Church Commissioners? | Bring up at Regional / National meetings. I can raise with Commissioners Rural team. | IT really should be possible for theCofE to provide model agreements for local adaptation! We now have confirmation of funding for the regional NZC collaboration and so, at least at that level, we should be able to have five dioceses inventing one wheel together. How much fo you already work with your E of England glebe colleagues? | 2022+ | 2025 |  | Normal policy review plus input from agents and third party church bodies, but depends how much co-operation there is |  | 4 |  | Agents / Church Commissioners | support staff costs / existing stafing budgets | n/a | n/a | nil | current budgets | [7 empty] | Glebe Officer | Assets Sub committee
6.2.0.6
6.2 Church land | Milestone | 6.2.6. Dioceses: All dioceses to align land management agreements going forward with the diocesan environmental policy objectives. | glebe | Can we piggy back off the Church Commissioners? | It will depend on the individual Diocesan environmental policy objective. | I agree it should largely be able to piggyback. We may have local objectives wrt peat and, perhaps, a greater emphasis on biodiversity. | 2025+ | 2025 |  | depends how much co-operation there is |  |  |  | Agents / Church Commissioners | support staff costs / existing stafing budgets | n/a | n/a | nil | current budgets | [7 empty] | Glebe Officer | Assets Sub committee
6.2 Church land | In Ely diocese | Look for biodiversity enhancement opportunities in all NZC planning | parish buildings | Further pushing the Cambs awards. Could also use REACH data to target advice to the frequent mowers? | DETG did not like my idea of Net Biodiv Gain, but I think we could develop something like this as a think-piece challenge | this is a kind of offsetting or Section 106, as well as Biodiv Net Gain; this needs working up // promoting Chyd Conservation Award; use REACH data to identify possible parishes | [5 empty] | 2
6.2.1.1
6.2 Church land | those responsible for land management should consider: | a. Reviewing with land agents the terms of tenancy agreements and use of the land. In terms of land use, a holistic approach that considers the benefits of increased carbon capture and biodiversity with food production and strategic value should be adopted. Opportunities to renegotiate terms with tenants should be investigated to support the take up of schemes which increase carbon storage and biodiversity. When new tenancies and licences are offered candidates with strong proposals in these areas should be given preferential consideration. | glebe | Highly relevant. Medium priority. Involves a set up of an informational framework. To be considered alongside basic economics of land rental. | viewed in the light of changing targets for land management agreements | It seems to me that the first step is to review our land agents. How up to speed are they, how much have they already taken this approach to heart, perhaps for other clients? A good agent who is already at the forefront of this shift will be able to manage this with rather little input from us - just wanting our direction to do this | 2025 | 2025 | [6 empty] | support staff costs / existing stafing budgets | n/a | n/a | nil | current budgets | n/a | n/a | n/a |  |  |  |  | Glebe Officer | Assets Sub committee
6.2.1.2
6.2 Church land | those responsible for land management should consider: | b. Where appropriate encourage greater carbon sequestration. It should be noted that this carbon may not contribute to the carbon budget of the landlord but be owned by the tenant as part of a scheme they have agreed to and be part of the business’ own carbon budget. It should also be noted that many of the schemes that would sequester significant amounts of carbon, such as certain types of tree planting, would not do so within the period before 2030, but sequestration will continue to be required. Planting now is valuable in biodiversity terms and provides for future carbon storage. | glebe | Highly relevant. Medium priority. Involves a set up of an informational framework. Will include input on ecological and environmental best practice. To be considered alongside basic economics of land rental. Plus possible central / joint Diocesan Arboretum or other such project. | Depends to an extent how you are required to measure. | This rather ignores peat. Tree planting, to make carbon sense, is a very longterm investment. I would love to estimate the embedded carbon in many tree-planting schemes. I suspect the payback time may be at least a decade if not more. | no | 2023+ |  | Some input in establishing frameworks and decision processes |  |  |  | Land agents could give extra time to these elements of management. | support staff costs / existing stafing budgets | DSF Capital to purchase central site | n/a | nil |  | DSF Capital account | [6 empty] | Glebe Officer | Assets Sub committee
6.2.1.3
6.2 Church land | In Ely diocese | Look for biodiversity enhancement opportunities in all NZC planning | glebe | Medium. Already in focus |  |  |  | 2023+ |  | Some input in establishing frameworks and decision processes |  | 2 |  | Land agents could give extra time to these elements of management. | likey in house resources | [7 empty] | potentially only full data comes from tenants. |  |  |  | Glebe Officer | Assets Sub committee
6.2 Church land | those responsible for land management should consider: | c. Land should be included within environmental policies by Church organisations so that where opportunities present themselves, such as with a change of tenant or sale/purchase of land, climate and biodiversity (and wider environmental gains such as flood prevention, soil improvement, temperature moderation, and air quality improvements) are considered as part of the process. It is not reasonable though to include this land in the net zero carbon target for 2030 because, for the greater proportion of landholdings, the Church organisations do not have the ability to directly change the management of it. | glebe | Important. I think land shound be included in targets if it belongs to the Church (glebe). Sensible to bring those concerns into focus. Need to review process for prioritisation of goals. Important to acknowlege the Church does not have control of much of the land directly. | Identify benchmark measuremtn tools. | It may not be 'in scope', but I agree that we should be working towards this from now on |  | 2023+ | Established a framework | Some input in establishing frameworks and decision processes |  |  |  | Land agents could give extra time to these elements of management. | from current in house resources | no | no | no |  |  |  |  | potentially only full data comes from tenants. |  |  |  | Glebe Officer | Assets Sub committee
6.2.1.4
6.2 Church land | those responsible for land management should consider: | d. Parishes to engage with opportunities to enhance the biodiversity of their churchyards through work such as that led by Caring for God’s Acre. For example, letting grass grow longer, in places where it doesn’t cause a health-and-safety hazard, can enhance biodiversity and store carbon, while reduced mowing frequency saves carbon emissions from mowing machinery. | parishes gen |  | Push the Wildlife Trust, 'Churchyard Conservation Scheme'. Part of media saturation in creationtide. + Part of Eco-Mailing | check with BCN WT over their capacity to respond; use early adopters to help promote [we shall need to watch the capacigy of the WT person to respond if there is a big increase in takeup] | [5 empty] | 7
6.2 Church land | In Ely diocese | Consider the potential for reduced carbon emissions from farmland on peat | glebe | Important we are to a greater extent dependant on many of our farming tenants. | depends on measurement process | the land audit should help us understand the extent of this for us. Soil carbon generally is a key C player and we are now only coming to recognise this - remember all the stubble burning in the 1980s! |  | 2022+ |  |  |  | 4 |  | fenland soil / other external specialist | support staff to deal with refocus of prncipal member of staff? | no | no | no | n/a | unlikely | n/a | n/a | potentially only full data comes from tenants. | no | no | Fenland Soil? | Glebe Officer | Assets Sub committee
7.1.0.3
7.1 Regular reporting | Milestone | 7.1.3. Dioceses: Dioceses to prepare a report on progress on the milestones detailing the successes and explaining the reasons for any delays to progress. To be submitted to the National Environment Team in Q1 that year to allow incorporation into the national report to General Synod in July. | parish buildings | Happy to contribute to this on church buildings. |  | this is for the strategy tab |  |  |  |  | 7 | 2 | 15
7.1 Regular reporting | Milestone | 7.1.3. Dioceses: Dioceses to prepare a report on progress on the milestones detailing the successes and explaining the reasons for any delays to progress. To be submitted to the National Environment Team in Q1 that year to allow incorporation into the national report to General Synod in July. | VA schools |  |  | I shall be coming back to you, Jacqueline, when we have to write this up. | 2025, 2028, 2031 |  |  | can be covered within existing resources | [16 empty] | Jacqueline McCamphill | Diocesan Board of Education
7.1.1.1
7.1 Regular reporting | Every diocese should consider: | 1. Requesting information from parishes and track progress against the Routemap to Net Zero Carbon by 2030 milestones on an annual basis. | parish buildings | Is this not primarily the EFT? | I think it is more than EFT. Have they got an action plan, a heat decarb plan, a heat resilience plan, for instance | this should not be an added burden for parishes beyond EFT // is there a useful 'tool' the diocese could provide that people want to use, but as they use it online they incidentally provide the data we are seeking: e.g. online action plan tool (sign in and share data), or a question ansering system (put in data and get a suggested answer). Are other dioceses doing this? Ignore the bottom 10 or 20% as very low users of energy. Organise a stratified sampling system. |  |  |  | NZC 5d | 5
7.1 Regular reporting | Every diocese should consider: | 1. Requesting information from parishes and track progress against the Routemap to Net Zero Carbon by 2030 milestones on an annual basis. | housing